2015-16 Malawi National Micronutrient Survey

Training and Field Manual

Component of Malawi Demographic and Health Survey

Malawi November 2015 – February 2016

Contents

ACROYNIMS AND ABBREVIATIONS	3

MODULE 1: GENERAL INFORMATION	5

Introduction	6

Background	6

Aims and objectives of the survey	7

Team composition and roles and responsibilities	9

Training	11

Sampling	12

Sampling and household enumeration	12

Overview of data collection materials	12

Overview of data collection	18

Handover from DHS to MN team	21

DHS and MN team logistics	27

Data Entry and Analysis	28

MODULE 1: GENERAL INFORMATION 	29

Annex 1.1: List of Selected Clusters	30

Annex 1.2: Transmittal form A	33

Annex 1.3: Training Schedule	37

Annex 1.4: Procedures for food collection	39

MODULE 2: INTERVIEWS	41

Human Rights and Consent Issues	42

Interview Techniques	42

Detailed instructions for questionnaire	48

MODULE 3: Anthropometry	50

MODULE 4: Data Management	63

# ACROYNIMS AND ABBREVIATIONS

AGP				1-acid glycoprotein

CDC	U.S. Centers for Disease Control and Prevention

CHSU	Community Health Sciences Unit

DHS	Demographic Health Survey

DNHA				Department for Nutrition, HIV and AIDS

Hb	Hemoglobin

HH	Household

NSO	National Statistics Office

sTfR	Soluble TransferrinReceptor

UNICEF			United Nations Children’s Fund

PSC				Preschool Children

SAC				School Age Children

WRA				Women of Reproductive Age

mRDT				Malaria Rapid Diagnostic Test

EA				Enumeration Area

# MODULE 1: GENERAL INFORMATION

# ALL SURVEY TEAM MEMBERS

## Introduction

This manual is for the Micronutrient (MN) team that will be implementing a micronutrient component of the Malawi Demographic Health Survey (MDHS).

This training manual is to serve as a detailed guide for the MN survey supervisors and the data collection team as the field work is implemented. The manual provides a detailed background and methodology for the survey as well as detailed information on how to conduct the field work. Included in this training manual is a step-by-step guide to implementing the questionnaire and all biological tests to be conducted.

This guide should be read carefully prior to the field work, and any questions should be discussed with the survey coordinator (Eunice Nyrendra), principal investigators (Isaac Chirwa, NSO, and Ben Chilima, CHSU), laboratory supervisor (Jellita Gondwe), and CDC technical support team (Parmi Suchdev, Carine Mapango, Katie Tripp, Stella Fagbemi, Elizabeth Rhode, and Anne Williams).

You should study this manual and learn its contents since this will reduce the amount of time needed for training and will improve your chances of being selected as a MN team member.

## Background

Demographic Health Survey

The 2015-16 Malawi Demographic and Health Survey (MDHS) is a national household survey designed to provide information on population, family planning, maternal and child health, child survival, HIV/AIDS and sexually transmitted infections (STIs), reproductive health, and nutrition in Malawi. The MDHS will involve interviewing a randomly selected group of respondents who are between 15 and 54 years of age. These respondents will be asked questions about their background, the children they have given birth to, their knowledge and use of family planning methods, the health of their children, their awareness of HIV/AIDS and sexually transmissible infections, and other information that will be helpful to policy makers and administrators in health and family planning fields. In one third of the households included in the MDHS the households will also have some biological specimens taken and tested for Hemoglobin level and HIV status. The micronutrient team will not visit any of these households.

For the 2015-16 Malawi DHS, the sample consists of 850 clusters (small geographically defined areas) from every district throughout the country. The households in each of these clusters have recently been enumerated. A sample of households was then randomly selected to be included in the 2015-16 Malawi DHS survey from the list in each of the clusters. The DHS expects to interview about 24,000 women and 7,500 men.

Micronutrient Survey

Micronutrient malnutrition and chronic malnutrition (stunting) are major public health problems in Malawi. There are also micronutrient deficiencies such as vitamin A, iron, zinc and iodine which can contribute to reduced immunity, impaired intellectual development and reduced work capacity. Increased morbidity and mortality, especially among women and children, is also associated with vitamin and mineral deficiencies.

There have been two national nutrition surveys conducted in Malawi, one in 2001 and another in 2009. The data from these surveys have been helpful to the government of Malawi, enabling them to identify needs, implement and monitor interventions, and advocate for additional programs and resources. Key nutrition interventions in Malawi include targeted micronutrient supplementation (vitamin A for under-five children and post-natal women within six weeks after delivery; iron and folate supplementation to pregnant women), nutrition education and food fortification of staple foods, such as oil and sugar with vitamin A and salt with iodine.

There is also a lack of data on other micronutrient deficiencies, such as zinc, which has an important role in child growth and immunity. The micronutrient survey is the first time such information will be collected in Malawi.  The survey findings will assess progress, evaluate existing programs, (such as the food fortification program), and provide a basis for policy direction, re-planning future interventions to accelerate actions towards the elimination of micronutrient deficiencies.

Information will be collected on household characteristics, including demographics, staple food purchase and socio-economic status. Biological specimens, in the form of venous blood samples will be collected from pre-school children aged 6 months 5 years and school aged children 6-14 years of age, women aged 15-49 years and men 20-54 years old within the household.  Urine samples will be collected from children 6-14 years old and women aged 15-49 years. Salt, sugar and oil samples will be collected from each household. Anthropometry (weight/height) will be measured on all participants.

This survey is being conducted by NSO, CHSU, DNHA, UNICEF with support and technical support from the US Centres for Disease Control and Prevention (CDC) and ICF macro.

## Aims and objectives of the nutritional component of the Demographic Health Survey

### Overall aim:

To assess the micronutrient status of the Malawian population

Specific Objectives

The specific objectives of the survey are:

- To estimate the prevalence of anaemia in Malawi.

- To estimate the prevalence of iron deficiency in Malawi.

- To estimate the prevalence of vitamin A deficiency in Malawi.

- To estimate the prevalence of iodine deficiency in Malawi.

- To estimate the prevalence of zinc deficiency in Malawi.

- To estimate the prevalence of vitamin B12 and folate deficiency in women of reproductive age in Malawi.

- To estimate the prevalence of inflammation in Malawi.

- To estimate the proportion of households with adequately iodized salt in Malawi.

- To estimate the proportion of households with fortified oil and sugar in Malawi.

- To estimate the prevalence of infection (malaria and urinary schistosomiasis) in Malawi.

- To estimate the prevalence of inherited blood disorders in children 6-59 months of age in Malawi.

- To determine the prevalence of wasting, stunting and underweight among preschool children and body mass index (BMI) of school-aged children, women and men in Malawi.

- To estimate the coverage of key nutrition interventions in Malawi

- To plan current and future nutrition interventions in Malawi

### Target Group

Target Groups

- Preschool children (PSC) aged 6-59 months

- School-aged children (SAC) aged 5-14 years

- Women of reproductive age (WRA) (non-pregnant and pregnant women) aged 15-49 years

- Men aged 20-55 years

Table 1: Summary of Nutrition Indicators by Target Group

| Group | Sample Size | Lab Indicators/Testing | Specimen Type & Materials |
| --- | --- | --- | --- |
| Preschool children (6-59 months) | 1,500 | Hb (field) Vit A, Iron (ELISA) Inflammation (ELISA) Zinc (lab) Malaria (Rapid test kit) Urinary Schisto (field) MRDR, retinol (n=100) Blood disorders (Dried blood spot) Anthropometry (height, weight, MUAC, odema) | Venous blood, urine dipstick, DBS Hemocue, blue top and purple top vacutainer, malaria RDK, urine dipstick, DBS |
| School-aged children (5-15 years) | 700 | Hb Vit A, Iron Inflammation Zinc Malaria Urinary Schisto Urinary iodine MRDR, retinol (n=100) Anthropometry (height, weight, MUAC) | Venous blood, urine dipstick, urine specimen |
| Women (15-49 years) | 780 | Hb Vit A, Iron Inflammation Zinc Folic Acid/B12 Malaria Urinary Schisto Urinary iodine MRDR, retinol (n=100) Anthropometry (height, weight, MUAC) | Venous blood, urine dipstick, urine specimen |
| Men (20 - 55 years) | 200 | Hb Vit A, Iron Inflammation Zinc Malaria Urinary Schisto Anthropometry (height, weight, MUAC) | Venous blood, urine dipstick |
| Household | 2,277 | Iodized salt Vit A sugar Vit A oil | Salt, sugar, oil |

## Team composition and roles and responsibilities

During the fieldwork, the field staff will work in an MN team consisting of six members.

- Supervisor

- Enumerator/Food & hygiene specialist

- 2 pediatric nurses

- 2 lab technicians

Each team will have two vehicles and will be accompanied by two drivers.

Team supervisor

- Understand all aspects of data collection and supervise its timely and correct implementation following all appropriate procedures specified in the field manual.

- Communicate with DHS teams on a daily basis.

- Keep in daily contact with the regional coordinator and survey coordinator during the field work.

- Request support from a community-based health worker for the cluster, if possible.

- Transfer relevant information from the questionnaire cover sheet to the Transmission form (FORM A).

- Make sure the necessary supplies and equipment are ready the night before each day of field work.

- Manage the work flow in the cluster and maintain all documentation regarding the completion of the cluster.

- Organize transportation or provide directions to the field lab for HHs members.

- Collect food samples from households.

- Ensure cold chain is maintained in the field.

- Oversee the work performance of the team members.

- Help ensure data quality, including:

  - Ensure labels are appropriately used and forms completed correctly.

  - Review all data collection forms for consistency and completeness.

  - Perform edits to the paper version micronutrient questionnaire in red ink. If missing values are identified, try to resolve them the following day while the team is in the cluster.

- Serve as a back-up for the team; assist team members if they need help.

- Ensure any difficulties with equipment/supplies are communicated to the survey coordinator as soon as possible

- Troubleshoot any problems with fieldwork.

- Remain flexible for accepting any reasonable tasks assigned that are not listed above.

Enumerator/Food and Hygiene staff

- Conduct the HH interview.

- Assign a lab ID and label the questionnaire columns for those eligible in the HH.

- Collect food samples from households.

- Transfer household members to the field lab.

Nurse

- Understand all aspects of data collection and supervise its timely and correct implementation following all appropriate procedures specified in the field manual.

# Serve as the primary phlebotomist for venous blood collection of survey participants.

# Conduct necessary field tests such as Hemocue, Anemocheck, rapid malaria kit and other field diagnostics as needed.

# Report results back to participants; refer and treat participants as needed.

# Perform anthropometry with laboratory technician.

# Conduct individual questionnaire of participants.

# Assist lab techs in setting up the field lab.

- Remain flexible for accepting any reasonable tasks assigned that are not listed above.

Laboratory Technician

- Secondary phlebotomist to assist nurse with venous blood collection.

- Perform anthropometry.

- Conduct testing for hemoglobin, malaria, urine dips stick in the household or field lab.

- Ensure Hemocues, freezers, centrifuge and other equipment are calibrated and functioning properly.

- Ensure that bio hazardous materials are disposed of properly and safely.

- Ensure proper sample labeling.

- Maintain cold chain at all times.

- Process samples as soon as possible after blood collection (centrifugation, separation, storage).

- Set up the field lab in each cluster.

- Prepare specimen collection kits.

In addition to the field teams there are 3 regional supervisors (1 for each region). These regional supervisors will ensure regular progress of data collection in the clusters. They will monitor data quality and provide for the regular transfer of completed questionnaires and bio specimens to CHSU (in Lilongwe).

Regional Coordinator

- Coordinate with study coordinator and DHS teams on all aspects of fieldwork.

- Establish timeframe for fieldwork and movement within and between clusters.

- Make regular visits to the teams in the field.

- Assist with maintaining records and cluster control sheets and corresponding sample labels

- Comply with the data tracking protocol.

- Oversee cold chain within region, including movement from clusters to regional storage freezers.

- Oversee shipment, transport of samples to central lab at CHSU in Lilongwe and other processing centers.

- Troubleshoot problems with fieldwork.

# Data editing staff and computer programmers also will be assigned to the project.

Figure 1. Team Organogram

## Training

In order to achieve the above objectives of the micronutrient survey, required survey training will be held for all staff between November 30th and December 7th 2015 at Chilema. Training will be all day from 8.30am until 5.30pm. Saturday will be full working day.

There will be two days of pilot testing, December 8-9th. Field work will begin on December 10th.

The objectives of the training workshop are:

- To train teams on the importance and rationale for national micronutrient surveys.

- To train teams on the various data collection tools for the Malawi national micronutrient survey.

- To improve the quality and reliability of micronutrient survey data collected in the field.

- To establish standardized data collection among teams through role plays and pilot testing of tools.

- To train teams on food specimen and biological sample collection, storage, processing, analyses, and transport of samples.

- To train teams on anthropometric data collection.

- To train on quality control and assurance procedures for survey tools.

- To explain the roles and responsibilities of individual and teams.

See Appendix 1.3 for the training schedule

## Sampling

## Sampling and household enumeration

The survey will be cross-sectional and stratified by three regions: North, South and Central followed by two stage cluster sampling within each strata.

The first stage involves selection of enumeration areas (EAs) and the second stage involves selection of households from the selected EAs.  In each strata (region), 35 EAs (105 total) have been randomly selected using probability proportional to population size. In each of the MN EA’s there will be 20 households selected in rural areas and 22 in urban areas. The households that will participate in the MN survey will participate in the DHS but will NOT be the DHS HHs where biological samples for the DHS will be collected. Among these selected households, a subsample of the households will be selected for various target groups for the micronutrient component (see Table below). All eligible participants living in that selected household will be approached for enrollment in the survey.

In each EA, households will be selected using a systematic random sampling method giving 759 households per strata and a total of 2277 households in the three strata for interviews and samples collection. The sampling frame will be based on the national census of 2008 population.

| Group | Target Sample Size | Sample per cluster | Households per cluster |
| --- | --- | --- | --- |
| PSC (6-59 months) | 1500 | 15 | 21 |
| SAC ( 5- <15 years) | 700 | 7 | 6 |
| WRA (15-49 years) | 780 | 8 | 9 |
| Men (20-55 years) | 200 | 2-3 | 4 |
| Total | 3180 |  | 2277 |

Data Collection Schematic per Cluster

| HH # |  | 1* | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| PSC |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X |
| SAC |  | X | X | X | X | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| WRA |  | X | X | X | X | X | X | X | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Men |  | X | X | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| MRDR test |  | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

## Overview of data collection materials

The primary data collection materials for the main field work are 1) questionnaire booklet and 2) labels

Questionnaire booklet

Each household will have a paper questionnaire booklet. The cover sheet will be partially pre-filled by the DHS (only the sections shaded grey). The remaining sections of the cover sheet should be filled by the MN team supervisor.

There are several sections in the questionnaire booklet.

Coversheet: This provides some basic information on the cluster, the household number, the number of participants eligible to participate (this information will come from a popup on the DHS tablets and will be filled by the DHS enumerator), consent for the MN team visit etc. The DHS enumerator and MN supervisor will complete the cover sheet.

Food fortification: This will be filled in by the MN enumerator. The enumerator will visit the HH and complete the food fortification section and collect any available food samples and label them.

Preschool child: There is space in the questionnaire to collect information on 6 preschool aged children. If there are more than 6 preschool aged children, then the DHS enumerator will have prepared a second questionnaire booklet for the HH.

The preschool aged children information will be recorded in a column format. There is space for information to be recorded on 3 children per page.

School-aged children: There is space in the questionnaire to collect information on 6 school aged children. If there are more than 6 school aged children then the DHS enumerator will have prepared a second questionnaire booklet for the HH.

The school-aged children information will be recorded in a column format. There is space for information to be recorded on 3 children per page.

Women of reproductive age: There is space in the questionnaire to collect information on 3 women of reproductive age. If there are more than 3 women of reproductive age then the DHS enumerator will have prepared a second questionnaire booklet for the HH.

The women of reproductive age information will be recorded in a column format. There is space for information to be recorded on 3 women of reproductive age per page.

Men: There is space in the questionnaire to collect information on 3 men. If there are more than 3 men then the DHS enumerator will have prepared a second questionnaire booklet for the HH.

The men information will be recorded in a column format. There is space for information to be recorded on 3 men per page.

Labels: There are several sets of labels. Different people will be responsible for working with the labels. The diagram below shows the various sets of labels and the flow of labels during the survey.

For each type of label there are several labels that will be used for each set. It is CRITICAL that for each set the same number series is used. The number on the label will tie the individual and the food and bio specimen to the HH and individual.

Household and food labels (Example of one set for one household. The next hosuehold would be 0002)

| MDHS 2015-16 HH Questionnaire IIIIIIIIIIIIIIIIIIII 0001 | MDHS 2015-16 Transmittal Form A IIIIIIIIIIIIIIIIIIII 0001 | MDHS 2015-16 |  |
| --- | --- | --- | --- |
|  |  | Oil container |  |
|  |  | IIIIIIIIIIIIIIIIIIII |  |
|  |  | 0001 |  |
| MDHS 2015-16 Salt container IIIIIIIIIIIIIIIIIIII 0001 | MDHS 2015-16 Sugar Container IIIIIIIIIIIIIIIIIIII 0001 | MDHS 2015-16 |  |
|  |  | Oil -Quest |  |
|  |  | IIIIIIIIIIIIIIIIIIII |  |
|  |  | 0001 |  |
| MDHS 2015-16 Salt-Quest. IIIIIIIIIIIIIIIIIIII 0001 | MDHS 2015-16 Sugar-Quest. IIIIIIIIIIIIIIIIIIII 0001 | MDHS 2015-16 |  |
|  |  | Extra |  |
|  |  | IIIIIIIIIIIIIIIIIIII |  |
|  |  | 0001 |  |

Preschool child label

| MDHS 2015-16 PSC 6-59 mo Bracelet IIIIIIIIIIIIIIIIIIII 5000 | MDHS 2015-16 PSC 6-59 mo Questionnaire IIIIIIIIIIIIIIIIIIII 5000 | MDHS 2015-16 PSC 6-59 mo Transmittal form B IIIIIIIIIIIIIIIIIIII 5000 |
| --- | --- | --- |
| MDHS 2015-16 PSC 6-59 mo Blue Top Vac IIIIIIIIIIIIIIIIIIII 5000 | MDHS 2015-16 PSC 6-59 mo Purple Top Vac IIIIIIIIIIIIIIIIIIII 5000 | MDHS 2015-16 PSC 6-59 mo MRDR Purple Top IIIIIIIIIIIIIIIIIIII 5000 |
| MDHS 2015-16 PSC 6-59 mo DBS sample IIIIIIIIIIIIIIIIIIII 5000 | MDHS 2015-16 PSC 6-59 mo Urine Cup IIIIIIIIIIIIIIIIIIII 5000 | MDHS 2015-16 PSC 6-59 mo Extra IIIIIIIIIIIIIIIIIIII 5000 |
| MDHS 2015-16 PSC 6-59 mo Transmittal form C IIIIIIIIIIIIIIIIIIII 5000 | MDHS 2015-16 PSC 6-59 mo Serum Vial 1 IIIIIIIIIIIIIIIIIIII 5000 | MDHS 2015-16 PSC 6-59 mo Serum Vial 3 IIIIIIIIIIIIIIIIIIII 5000 |
| MDHS 2015-16 PSC 6-59 mo Plasma Vial 1 IIIIIIIIIIIIIIIIIIII 5000 | MDHS 2015-16 PSC 6-59 mo Extra IIIIIIIIIIIIIIIIIIII 5000 | MDHS 2015-16 PSC 6-59 mo Extra IIIIIIIIIIIIIIIIIIII 5000 |

School-aged child label

| MDHS 2015-16 SAC 5-14 yrs Bracelet IIIIIIIIIIIIIIIIIIII 7000 | MDHS 2015-16 SAC 5-14 yrs Questionnaire IIIIIIIIIIIIIIIIIIII 7000 | MDHS 2015-16 SAC 5-14 yrs Transmittal form B IIIIIIIIIIIIIIIIIIII 7000 |
| --- | --- | --- |
| MDHS 2015-16 SAC 5-14 yrs Blue Top Vac IIIIIIIIIIIIIIIIIIII 7000 | MDHS 2015-16 SAC 5-14 yrs Purple Top Vac IIIIIIIIIIIIIIIIIIII 7000 | MDHS 2015-16 SAC 5-14 yrs MRDR Purple Top IIIIIIIIIIIIIIIIIIII 7000 |
| MDHS 2015-16 SAC 5-14 yrs Urine Cup IIIIIIIIIIIIIIIIIIII 7000 | MDHS 2015-16 SAC 5-14 yrs Urine Vial 1 IIIIIIIIIIIIIIIIIIII 7000 | MDHS 2015-16 SAC 5-14 yrs Urine Vial 2 IIIIIIIIIIIIIIIIIIII 7000 |
| MDHS 2015-16 SAC 5-14 yrs Transmittal form C IIIIIIIIIIIIIIIIIIII 7000 | MDHS 2015-16 SAC 5-14 yrs Serum Vial 1 IIIIIIIIIIIIIIIIIIII 7000 | MDHS 2015-16 SAC 5-14 yrs Serum Vial 3 IIIIIIIIIIIIIIIIIIII 7000 |
| MDHS 2015-16 SAC 5-14 yrs Plasma Vial 1 IIIIIIIIIIIIIIIIIIII 7000 | MDHS 2015-16 SAC 5-14 yrs Extra IIIIIIIIIIIIIIIIIIII 7000 | MDHS 2015-16 SAC 5-14 yrs Extra IIIIIIIIIIIIIIIIIIII 7000 |

Women labels

| MDHS 2015-16 WRA 15-49 yrs Bracelet IIIIIIIIIIIIIIIIIIII 8000 | MDHS 2015-16 WRA 15-49 yrs Questionnaire IIIIIIIIIIIIIIIIIIII 8000 | MDHS 2015-16 WRA 15-49 yrs Transmittal form B IIIIIIIIIIIIIIIIIIII 8000 |
| --- | --- | --- |
| MDHS 2015-16 WRA 15-49 yrs Blue Top Vac IIIIIIIIIIIIIIIIIIII 8000 | MDHS 2015-16 WRA 15-49 yrs Purple Top Vac IIIIIIIIIIIIIIIIIIII 8000 | MDHS 2015-16 WRA 15-49 yrs MRDR Purple Top IIIIIIIIIIIIIIIIIIII 8000 |
| MDHS 2015-16 WRA 15-49 yrs Urine Cup IIIIIIIIIIIIIIIIIIII 8000 | MDHS 2015-16 WRA 15-49 yrs Urine Vial 1 IIIIIIIIIIIIIIIIIIII 8000 | MDHS 2015-16 WRA 15-49 yrs Urine Vial 2 IIIIIIIIIIIIIIIIIIII 8000 |
| MDHS 2015-16 WRA 15-49 yrs Transmittal form C IIIIIIIIIIIIIIIIIIII 8000 | MDHS 2015-16 WRA 15-49 yrs Serum Vial 1 IIIIIIIIIIIIIIIIIIII 8000 | MDHS 2015-16 WRA 15-49 yrs Serum Vial 2 IIIIIIIIIIIIIIIIIIII 8000 |
| MDHS 2015-16 WRA 15-49 yrs Serum Vial 3 IIIIIIIIIIIIIIIIIIII 8000 | MDHS 2015-16 WRA 15-49 yrs Plasma Vial 1 IIIIIIIIIIIIIIIIIIII 8000 | MDHS 2015-16 WRA 15-49 yrs RBC Fol Vial 1 IIIIIIIIIIIIIIIIIIII 8000 |
| MDHS 2015-16 WRA 15-49 yrs RBC Fol Vial 2 IIIIIIIIIIIIIIIIIIII 8000 | MDHS 2015-16 WRA 15-49 yrs Extra IIIIIIIIIIIIIIIIIIII 8000 | MDHS 2015-16 WRA 15-49 yrs Extra IIIIIIIIIIIIIIIIIIII 8000 |

Men labels

| MDHS 2015-16 Men 20-55 yrs Bracelet IIIIIIIIIIIIIIIIIIII 9000 | MDHS 2015-16 Men 20-55 yrs Questionnaire IIIIIIIIIIIIIIIIIIII 9000 | MDHS 2015-16 Men 20-55 yrs Transmittal form B IIIIIIIIIIIIIIIIIIII 9000 |
| --- | --- | --- |
| MDHS 2015-16 Men 20-55 yrs Blue Top Vac IIIIIIIIIIIIIIIIIIII 9000 | MDHS 2015-16 Men 20-55 yrs Purple Top Vac IIIIIIIIIIIIIIIIIIII 9000 | MDHS 2015-16 Men 20-55 yrs Urine Cup IIIIIIIIIIIIIIIIIIII 9000 |
| MDHS 2015-16 Men 20-55 yrs Transmittal form C IIIIIIIIIIIIIIIIIIII 9000 | MDHS 2015-16 Men 20-55 yrs Serum Vial 1 IIIIIIIIIIIIIIIIIIII 9000 | MDHS 2015-16 Men 20-55 yrs Serum Vial 3 IIIIIIIIIIIIIIIIIIII 9000 |
| MDHS 2015-16 Men 20-55 yrs Plasma Vial 1 IIIIIIIIIIIIIIIIIIII 9000 | MDHS 2015-16 Men 20-55 yrs Extra IIIIIIIIIIIIIIIIIIII 9000 | MDHS 2015-16 Men 20-55 yrs Extra IIIIIIIIIIIIIIIIIIII 9000 |

## Overview of data collection

The main steps for the MN component of the survey are outlined in the figure below.

Step 1: The DHS will visit the cluster and complete data collection entirely. A detailed description of the handover process can be found below. Once DHS has prepared the questionnaires for the MN team, the MN supervisor and the DHS supervisor will conduct the handover.

Step 2: The MN supervisor will then prepare the transmittal sheet based on the data recorded on the cover sheet of the questionnaire. They will then hand over the transmittal sheet and the questionnaires to the enumerator.

Step 3: The enumerator will visit each of the households in turn. On arrival at the household they will explain the purpose of the survey to the head of household. They will then conduct the food fortification section of the questionnaire and collect food samples where possible. The foods of interest are salt, sugar and oil. Any household providing these samples will have their samples replaced. The enumerator will collect any samples they have of these three items and then label the sample and the questionnaire. See annex 1.4 for procedures for food specimen collection.

Once the food fortification module is complete the enumerator will review the number of eligible participants in the household. The number of eligible people will be written on the cover of the questionnaire and on the cover sheet.

The participant section of the questionnaire will also have some detials on the eligible individuals. For Example below is the upper part of the preschool child questionnaire. The section in grey will have been prefilled by the DHS enumerator. You can see in the example below that in this household there is only one eligible pre-school child called Maria. The eumerator will ask the mother for Maria’s date of birth and then place the Questionnaire label in the space circled.

Maria

0

1

Each target groups will have a whole set of labels. All the labels for the SAME person will have the same ID. The ID is what links the individual to the questionnaire and the results of their biological tests.

Below is an example of one sheet of labels that will be used for 1 preschool child. There are 18 in total. For the remining kids there will be sheets of labels, each also with 18 labels. For each child only the first two labels will be used in the household. One will be placed on the bracelet and the other in the correspnding coloumn for that child in the questionnaire booklet. The enumerator will place the questionnaire label on the questionnaire (see below). Next, they will take a green ID bracelet, put the “bracelet” label on the bracelet, and place the bracelet on the child’s wrist. Make sure the bracelet is put on properly so that it fits the child and will not slip off. It should not be too tight or too loose.

Labels for PSC 6-59 months MDHS 2015 PSC 6-59 mo Bracelet IIIIIIIIIIIIIIIIIIII PSC001; MDHS 2015 PSC 6-59 mo Lab Questionnaire IIIIIIIIIIIIIIIIIIII PSC001; MDHS 2015 PSC 6-59 mo Transmittal form C IIIIIIIIIIIIIIIIIIII PSC001. MDHS 2015 PSC 6-59 mo Blue Top Vac IIIIIIIIIIIIIIIIIIII PSC001; MDHS 2015 PSC 6-59 mo Purple Top Vac IIIIIIIIIIIIIIIIIIII PSC001; MDHS 2015 PSC 6-59 mo MRDR Purple Top IIIIIIIIIIIIIIIIIIII PSC001. MDHS 2015 PSC 6-59 mo Urine Cup IIIIIIIIIIIIIIIIIIII PSC001; MDHS 2015 PSC 6-59 mo DBS sample IIIIIIIIIIIIIIIIIIII PSC001; MDHS 2015 PSC 6-59 mo Malaria Ref Log IIIIIIIIIIIIIIIIIIII PSC001. MDHS 2015 PSC 6-59 mo Hgb Ref Log IIIIIIIIIIIIIIIIIIII PSC001; MDHS 2015 PSC 6-59 mo Schisto Ref Log IIIIIIIIIIIIIIIIIIII PSC001; MDHS 2015 PSC 6-59 mo Extra IIIIIIIIIIIIIIIIIIII PSC001. MDHS 2015 PSC 6-59 mo Transmittal form D IIIIIIIIIIIIIIIIIIII PSC001; MDHS 2015 PSC 6-59 mo Serum Vial 1 IIIIIIIIIIIIIIIIIIII PSC001; MDHS 2015 PSC 6-59 mo Serum Vial 3 IIIIIIIIIIIIIIIIIIII PSC001. MDHS 2015 PSC 6-59 mo Plasma Vial 1 IIIIIIIIIIIIIIIIIIII PSC001; MDHS 2015 PSC 6-59 mo Extra IIIIIIIIIIIIIIIIIIII PSC001; MDHS 2015 PSC 6-59 mo Extra IIIIIIIIIIIIIIIIIIII PSC001.

ID bracelet

The remaining labels (16 of them) will be stapled to the back cover of the questionnaire booklet. When the questionnaire reaches the field lab the labels will be used by the nurse and the lab tech.

Once all the eligible participants have been labelled, the enumerator will transfer them to the field lab. This might be walking or via one of the team vehicles.

Step 4: Once the enumerator arrives at the field lab with the HH participants, they will give the questionnaire (which will have all the relevant labels stapled inside it) to the nurse. The nurse will then conduct individual consent and continue with the questions for each of the participants. After the interview is complete she will take the participants blood sample and ask them for a urine sample. The field tests (hemoglobin, malaria, AnemoCheck and DBS (for some target groups) will be conducted. The biological specimens will be handed off to the lab tech for processing. The participants will them be measured and assessed for oedema. The relevant labels will be used by the nurse and lab tech for the tests they are conducting.

Step 5: The lab tech will take the biological samples and the remaining labels and begin processing the samples. [see lab manual for more details]

Step 6: The specimens will be taken in the portable freezer to the nearest district level facility that has been identified as a cold chain location. The team leader will be charge of this.

Step 7: The specimens from the district level facilities will be transported to CHSU on a bi monthly basis.

Step 8: The questionnaires and the data from the transmittal sheet will be double data entered back at the facility in Zomba.

## Handover from DHS to MN team

DHS completing the cover sheet and target group information for the MN households

Once the MDHS team has finished the data collection in a HH, an output will pop up on their tablet with the information that needs to be written on the MN questionnaire and the transmittal sheet. The DHS has 4 enumerators per team and one team per cluster. Some urban areas might have two teams per district. Each enumerator will need several sets of the MN Household/food sample labels and some of the MN Questionnaires.

In MN households, once the DHS have finished their data collection and they have the popup output with who is eligible they will complete the coverage of the paper based questionnaires and the top section of the target group pages depending on which target groups will be included in which household. This will already be programmed into the tablets and the DHS enumerators will just need to transfer the information from the popup screen. They will use the household labels provided by the MN survey supervisor and will put a label on the questionnaire and then type that HH barcode number into the tablet. They will type in the label twice. If the second entry does not match the first an error message will come up to prompt them to double check the label and enter it again correctly. This number will link all of the data from the DHS to the MN survey. The DHS enumerator will then staple the remaining 8 labels for that household to the back page of the questionnaire.

MDHS will obtain consent for the MN team to visit

Once the cover page and the target group sections have been completed by the DHS team, the DHS team will ask the household to consent to having a nutrition team visit the household.

Information provided to household head from the DHS team

In the next few days, my colleagues who are working with the ministry of health would like to revisit your household to conduct a micronutrient study. The micronutrient team will collect samples of sugar, oil, and salt used in the household; conduct a brief interview to assess individual and household-level exposures to nutrition interventions; and collect venous blood and urine samples to evaluate micronutrient status of children aged 6-59 months, school-age children (6-14 years), women age 15-49 years, and men age 20-54 years.  You don't have to permit the visit, but we hope you will agree since your household participation is very important. In case you need more information about the revisit, you may contact the person listed on this card.

GIVE CARD WITH CONTACT INFORMATION

Do you have any questions?

Do you agree for your household to be revisited?

If the household agrees to participate in the micronutrient survey, then the micronutrient team can visit the household and administer the questionnaire and survey protocol. If the household refuses to participate, then that household should not be approached by the micronutrient team. The cover page of the questionnaire will state that the HH refused or it they agreed. This information will also be written on the transmittal form by the MN team lead.

To avoid having low response rates, it is critical that the DHS team understand the importance and value of the MN survey. This should be thoroughly explained during the DHS training.

Timing of handover

Unless there are significant timing issues the MN team will not start in a cluster until the DHS is complete. There are several reasons: 1) the cover sheet for the MN questionnaire can only be complete once a DHS questionnaire is completely finalized, as only then will all the DHS information be collected and the MN cover page be generated; 2) it can take a few days for a DHS household to be completed and if the micronutrient team starts with only 1-3 household complete they might be waiting for days in between for the next household to be complete; 3) There will be far less opportunity for error if the complete set of questionnaires are handed over from the DHS supervisor to the MN supervisor and there is complete handover.

Both the DHS and nutrition team agree to do the handover once DHS is ready to leave the cluster

The DHS will hand over 1) MN questionnaires with cover sheets and grey areas of participant questionnaire complete, 2) the output print out from all of the MN households, 3) map of the EA with HHs marked

Hand over from DHS Supervisor to MN Supervisor

Once the entire cluster is complete the DHS supervisor will collect all the questionnaires. The DHS supervisor will also get a print out of all the information for all the MN households in the whole cluster, which he will give to the MN team lead. The DHS supervisor will check over the questionnaires and the overall print out to make sure there are no errors. The questionnaires will be handed over to the MN team lead.

The Micronutrient questionnaire comes in a booklet format. The DHS enumerator will complete the top section (in grey) at the top of the sections for each target group that will be included in that household. The popup from the tablet will indicate which target groups to include.

The MN team lead will take all the questionnaire booklets. In Rural clusters there should be no less than 20 booklets and in Urban clusters 22. The team lead will then complete the transmittal sheet [FORM A] – see below.

Form A is intended to be a management tool for the team leader. It will list the cluster and household and date. It will list all the households in the cluster and how many of each target group are eligible to be included in the cluster. There will also be space for the “transmittal form label”.

Transmittal form A

HH IDENTIFICATION

CLUSTER (EA) NUMBER CLUSTER (EA) NAME

DHS Supervisor No. MN team lead No: MN enumerator ID

#; DHS HH No (write in from coversheet); Place HH Barcode label here; Field Notes (Record additional respondent information). HH Visit# (check); Eligible PSC; Eligible SAC; Eligible WRA; Eligible Men; Food Sample collection. # in HH; # complete; # in HH; # complete; # in HH; # complete; # in HH; # complete; Salt; Sugar; Oil. 1; 2. 1. 2. 3. 4. 5.

In the top section of the form the team lead will fill in the following:

CLUSTER (EA) NUMBER CLUSTER (EA) NAME

DHS Supervisor No. MN team lead No: MN enumerator ID

In the main body of the form the team lead will use the information from the questionnaire cover sheet to transfer the information to the form. The first column will be the HH number. This is the HH number that DHS will write on the questionnaire cover sheet. The MN team lead will go to the back of that questionnaire and place the transmittal form label. The team lead will then fill in the number of eligible people. This information is on the front of the cover sheet.

Once the team lead has done this for each household the forms can be passed on to the enumerator who will then start to visits the households.

| # | DHS HH No (write in from coversheet) | Place HH Barcode label here |  |  |  |  |  |  |  |  |  |  |  |  |  | Field Notes (Record additional respondent information) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | HH Visit# (check) |  | Eligible PSC |  | Eligible SAC |  | Eligible WRA |  | Eligible Men |  | Food Sample collection |  |  |  |
|  |  |  |  |  | # in HH | # complete | # in HH | # complete | # in HH | # complete | # in HH | # complete | Salt | Sugar | Oil |  |
|  |  |  | 1 | 2 |  |  |  |  |  |  |  |  |  |  |  |  |
| 1 | 15 | MDHS 2015-16 Transmittal Form A IIIIIIIIIIIIIIIIIIII 0001. |  |  | 2 |  | 1 |  | 1 |  | 1 |  |  |  |  |  |
| 2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

SUMMARY OF MAIN STEPS FOR THE HANDOVER

DHS enumerator completes household and transfers popup information to MN questionnaire

DHS enumerator labels the MN questionnaire and enters label number into tablet

Staples remaining labels to back cover of Questionnaire

DHS enumerator conducts consent for MN visit

DHS supervisor checks questionnaires will overall output and hands over MN questionnaires to MN supervisor

MN supervisor prepares the transmittal sheet [form A]

## DHS and MN team logistics

There are 27 districts in Malawi and the DHS will have 37 teams. Each district will have 1 DHS team assigned and the extra teams will be assigned to the more urban areas. There will be 5 MN teams. Each MN team will need to complete 17 or 18 clusters. They will be assigned to work with several DHS teams. This will vary depending on the number of clusters selected per district.

The DHS will start before the MN survey. The DHS will do the non-MN clusters first. Once the MN teams are in place the DHS teams they are assigned to will take it in turns to do their MN clusters.  The team leads (from DHS and MN teams) and the regional supervisors and NSO will work together to group the DHS districts with the MN teams. Once the groups have been agreed they will work out an itinerary for the DHS teams and the assigned MN team to ensure that the MN clusters are spaced in a way that will ensure that the MN team will be able to get to the next MN cluster just as that DHS team is leaving. There must not be a delay in the handover, so the itinerary and coordination between the DHS teams and MN team is essential.

The NSO field supervisor will be in charge of this and will also coordinate with the MN regional lab supervisor and the MN survey coordinator.

Routing for each MN team

For each MN team it is critical to know how many clusters within each district is a micronutrient cluster. It needs to be decided ahead of time which district(s) will start their MN clusters first. The pace of the DHS teams is very important because the goal for the MN team is one cluster every 2 days. If the DHS takes 4 days a cluster then two districts will need to start at the same time so that the MN team isn’t waiting. Once there is a sense of the DHS team pace a decision will need to be made about the logistics of fitting in the MN team and making sure there are no gaps.

Example of a team itinerary

| DATE | DAY OF THE WEEK | DISTRICT | MNS TEAM 1 CLUSTERNUMBER | DHS TEAM |
| --- | --- | --- | --- | --- |
| 11-Dec | Friday | CHITIPA | 2 | 1 |
| 12-Dec | Saturday | CHITIPA | 2 | 1 |
| 14-Dec | Monday | KARONGA | 26 | 2 |
| 15-Dec | Tuesday | KARONGA | 26 | 2 |
| 16-Dec | Wednesday | CHITIPA | 10 | 1 |
| 17-Dec | Thursday | CHITIPA | 10 | 1 |
| 18-Dec | Friday | CHITIPA | 10 | 1 |
| 19-Dec | Saturday | KARONGA | 30 | 2 |
| 21-Dec | Monday | KARONGA | 30 | 2 |
| 22-Dec | Tuesday | CHITIPA | 18 | 1 |
| 23-Dec | Wednesday | CHITIPA | 18 | 1 |
| 24-Dec | Thursday | CHITIPA | 18 | 1 |
| 25-Dec | Friday | KARONGA | 34 | 2 |
| 26-Dec | Saturday | KARONGA | 34 | 2 |
| 28-Dec | Monday | CHITIPA | 6 | 1 |
| 29-Dec | Tuesday | CHITIPA | 6 | 1 |
| 30-Dec | Wednesday | KARONGA | 38 | 2 |
| 31-Dec | Thursday | KARONGA | 38 | 2 |
| 1-Jan | Friday | KARONGA | 38 | 2 |

See appendix 1.1 for the complete list of MN clusters

## Data Entry and Analysis

During the survey, paper questionnaire booklets will be collected, edited, and double-entered into a computer database.  The MNMS data manager will oversee data entry and management in coordination with the NSO. Any errors in completing questionnaires will be corrected in the field where possible.  To reduce computer data entry error, the entry screen will be programmed to accept only codes within a pre-determined range.  All data will also be double entered and verified.  Once the data has been double entered, the report prepared and presented, the completed questionnaires will be destroyed.

# MODULE 1: GENERAL INFORMATION ANNEXES

# 1.1 LIST OF SELECTED CLUSTERS

# 1.2 TRANSMITTAL FORM A

# 1.3 TRAINING SCHEDULE

# 1.4 PROCEDURES FOR FOOD COLLECTION

## Annex 1.1: List of Selected Clusters

| Cluster number | Region | Region name | District | Dist name | Dist_strat1 | TA2 | TA Names | Urban/Rural |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 2 | 1 | North | 101 | Chitipa | Chitipa | 10101 | Mwabulambya | Rural |
| 6 | 1 | North | 101 | Chitipa | Chitipa | 10101 | Mwabulambya | Rural |
| 10 | 1 | North | 101 | Chitipa | Chitipa | 10102 | Mwenemisuku | Rural |
| 14 | 1 | North | 101 | Chitipa | Chitipa | 10103 | Mwenewenye | Rural |
| 18 | 1 | North | 101 | Chitipa | Chitipa | 10104 | Nthalire | Rural |
| 22 | 1 | North | 101 | Chitipa | Chitipa | 10120 | Chitipa Boma | Urban |
| 26 | 1 | North | 102 | Karonga | Karonga | 10201 | Kilupula | Rural |
| 30 | 1 | North | 102 | Karonga | Karonga | 10201 | Kilupula | Rural |
| 34 | 1 | North | 102 | Karonga | Karonga | 10203 | Kyungu | Rural |
| 38 | 1 | North | 102 | Karonga | Karonga | 10203 | Kyungu | Rural |
| 42 | 1 | North | 102 | Karonga | Karonga | 10204 | Wasambo | Rural |
| 46 | 1 | North | 102 | Karonga | Karonga | 10220 | Karonga town | Urban |
| 50 | 1 | North | 102 | Karonga | Karonga | 10220 | Karonga town | Urban |
| 54 | 1 | North | 103 | Nkhatabay | Nkhatabay | 10301 | Kabunduli | Rural |
| 58 | 1 | North | 103 | Nkhatabay | Nkhatabay | 10302 | Fukamapiri | Rural |
| 62 | 1 | North | 103 | Nkhatabay | Nkhatabay | 10304 | S/C Malanda | Rural |
| 66 | 1 | North | 103 | Nkhatabay | Nkhatabay | 10306 | Mankhambira | Rural |
| 70 | 1 | North | 103 | Nkhatabay | Nkhatabay | 10309 | Musisya | Rural |
| 74 | 1 | North | 103 | Nkhatabay | Nkhatabay | 10312 | Timbiri | Rural |
| 78 | 1 | North | 103 | Nkhatabay | Nkhatabay | 10320 | Nkhata Bay Boma | Urban |
| 82 | 1 | North | 104 | Rumphi | Rumphi | 10401 | Chikulamayembe | Rural |
| 86 | 1 | North | 104 | Rumphi | Rumphi | 10401 | Chikulamayembe | Rural |
| 90 | 1 | North | 104 | Rumphi | Rumphi | 10402 | Mwamlomwe | Rural |
| 94 | 1 | North | 104 | Rumphi | Rumphi | 10404 | S/C Mwalweni | Rural |
| 98 | 1 | North | 104 | Rumphi | Rumphi | 10407 | S/C Mwankhunikira | Rural |
| 102 | 1 | North | 104 | Rumphi | Rumphi | 10420 | Rumphi boma | Urban |
| 106 | 1 | North | 104 | Rumphi | Rumphi | 10420 | Rumphi boma | Urban |
| 110 | 1 | North | 105 | Mzimba | Mzimba | 10501 | M'mbelwa | Rural |
| 114 | 1 | North | 105 | Mzimba | Mzimba | 10502 | Mtwalo | Rural |
| 118 | 1 | North | 105 | Mzimba | Mzimba | 10505 | Chindi | Rural |
| 122 | 1 | North | 105 | Mzimba | Mzimba | 10505 | Chindi | Rural |
| 126 | 1 | North | 105 | Mzimba | Mzimba | 10507 | Mabulabo | Rural |
| 131 | 1 | North | 105 | Mzimba | Mzimba | 10520 | Mzimba Boma | Urban |
| 135 | 1 | North | 107 | Mzuzu City | Mzimba | 10734 | Mzuzu City_Chiputula Ward | Urban |
| 139 | 1 | North | 107 | Mzuzu City | Mzimba | 10741 | Mzuzu City_Katawa Ward | Urban |
| 165 | 2 | Central | 201 | Kasungu | Kasungu | 20101 | Kaluluma | Rural |
| 173 | 2 | Central | 201 | Kasungu | Kasungu | 20107 | S/C Kawamba | Rural |
| 181 | 2 | Central | 201 | Kasungu | Kasungu | 20111 | Santhe | Rural |
| 189 | 2 | Central | 201 | Kasungu | Kasungu | 20115 | Mwase | Rural |
| 198 | 2 | Central | 202 | Nkhota kota | Nkhota kota | 20201 | Kanyenda | Rural |
| 206 | 2 | Central | 202 | Nkhota kota | Nkhota kota | 20203 | Malengachanzi | Rural |
| 214 | 2 | Central | 202 | Nkhota kota | Nkhota kota | 20205 | Mwadzama | Rural |
| 222 | 2 | Central | 202 | Nkhota kota | Nkhota kota | 20220 | Nkhotakota Boma | Urban |
| 230 | 2 | Central | 203 | Ntchisi | Ntchisi | 20303 | S/C Nthondo | Rural |
| 238 | 2 | Central | 203 | Ntchisi | Ntchisi | 20305 | S/C Chilooko | Rural |
| 246 | 2 | Central | 203 | Ntchisi | Ntchisi | 20306 | Malenga | Rural |
| 254 | 2 | Central | 204 | Dowa | Dowa | 20401 | Dzoole | Rural |
| 262 | 2 | Central | 204 | Dowa | Dowa | 20403 | S/C Kayembe | Rural |
| 271 | 2 | Central | 204 | Dowa | Dowa | 20405 | S/C Mkukula | Rural |
| 279 | 2 | Central | 204 | Dowa | Dowa | 20407 | S/C Mponela | Rural |
| 287 | 2 | Central | 205 | Salima | Salima | 20501 | Maganga | Rural |
| 295 | 2 | Central | 205 | Salima | Salima | 20504 | S/C Kambwiri | Rural |
| 303 | 2 | Central | 205 | Salima | Salima | 20507 | Khombedza | Rural |
| 311 | 2 | Central | 205 | Salima | Salima | 20520 | Salima Town | Urban |
| 319 | 2 | Central | 206 | Lilongwe Rural | Lilongwe | 20603 | Chiseka | Rural |
| 327 | 2 | Central | 206 | Lilongwe Rural | Lilongwe | 20606 | Khongoni | Rural |
| 335 | 2 | Central | 206 | Lilongwe Rural | Lilongwe | 20615 | Kabudula | Rural |
| 344 | 2 | Central | 210 | Lilongwe City | Lilongwe | 21066 | Area 36 | Urban |
| 352 | 2 | Central | 207 | Mchinji | Mchinji | 20701 | Mlonyeni | Rural |
| 360 | 2 | Central | 207 | Mchinji | Mchinji | 20703 | Zulu | Rural |
| 368 | 2 | Central | 207 | Mchinji | Mchinji | 20704 | S/C Nduwa | Rural |
| 376 | 2 | Central | 207 | Mchinji | Mchinji | 20706 | S/C Dambe | Rural |
| 384 | 2 | Central | 208 | Dedza | Dedza | 20801 | Pemba | Rural |
| 392 | 2 | Central | 208 | Dedza | Dedza | 20803 | S/C Kaphuka | Rural |
| 400 | 2 | Central | 208 | Dedza | Dedza | 20804 | Tambala | Rural |
| 408 | 2 | Central | 208 | Dedza | Dedza | 20807 | Kachindamoto | Rural |
| 417 | 2 | Central | 209 | Ntcheu | Ntcheu | 20901 | Phambala | Rural |
| 425 | 2 | Central | 209 | Ntcheu | Ntcheu | 20904 | S/C Makwangwala | Rural |
| 433 | 2 | Central | 209 | Ntcheu | Ntcheu | 20906 | Njolomole | Rural |
| 441 | 2 | Central | 209 | Ntcheu | Ntcheu | 20908 | S/C Goodson Ganya | Rural |
| 458 | 3 | South | 301 | Mangochi | Mangochi | 30103 | Nankumba | Rural |
| 470 | 3 | South | 301 | Mangochi | Mangochi | 30106 | S/C Chowe | Rural |
| 482 | 3 | South | 301 | Mangochi | Mangochi | 30120 | Mangochi Town | Urban |
| 493 | 3 | South | 302 | Machinga | Machinga | 30203 | Kawinga | Rural |
| 505 | 3 | South | 302 | Machinga | Machinga | 30208 | S/C Ngokwe | Rural |
| 516 | 3 | South | 303 | Zomba Rural | Zomba | 30301 | Kuntumanji | Rural |
| 528 | 3 | South | 303 | Zomba Rural | Zomba | 30305 | S/C Mbiza | Rural |
| 539 | 3 | South | 303 | Zomba Rural | Zomba | 30307 | Malemia | Rural |
| 551 | 3 | South | 304 | Chiradzulu | Chiradzulu | 30401 | Mpama | Rural |
| 562 | 3 | South | 304 | Chiradzulu | Chiradzulu | 30403 | Kadewere | Rural |
| 574 | 3 | South | 304 | Chiradzulu | Chiradzulu | 30406 | Nchema | Rural |
| 585 | 3 | South | 305 | Blantyre Rural | Blantyre | 30504 | Kunthembwe | Rural |
| 597 | 3 | South | 315 | Blantyre City | Blantyre | 31534 | Nkolokoti Ward | Urban |
| 608 | 3 | South | 315 | Blantyre City | Blantyre | 31548 | Limbe East Ward | Urban |
| 620 | 3 | South | 306 | Mwanza | Mwanza | 30601 | Kanduku | Rural |
| 631 | 3 | South | 306 | Mwanza | Mwanza | 30602 | Nthache | Rural |
| 643 | 3 | South | 307 | Thyolo | Thyolo | 30703 | S/C Mbawela | Rural |
| 654 | 3 | South | 307 | Thyolo | Thyolo | 30708 | Nchilamwela | Rural |
| 666 | 3 | South | 307 | Thyolo | Thyolo | 30710 | Bvumbwe | Rural |
| 677 | 3 | South | 308 | Mulanje | Mulanje | 30801 | Mabuka | Rural |
| 689 | 3 | South | 308 | Mulanje | Mulanje | 30803 | Chikumbu | Rural |
| 700 | 3 | South | 308 | Mulanje | Mulanje | 30806 | S/C Juma | Rural |
| 712 | 3 | South | 309 | Phalombe | Phalombe | 30901 | Mnkhumba | Rural |
| 723 | 3 | South | 309 | Phalombe | Phalombe | 30901 | Mnkhumba | Rural |
| 735 | 3 | South | 309 | Phalombe | Phalombe | 30920 | Phalombe Boma | Urban |
| 746 | 3 | South | 310 | Chikwawa | Chikwawa | 31002 | Lundu | Rural |
| 758 | 3 | South | 310 | Chikwawa | Chikwawa | 31006 | Kasisi | Rural |
| 769 | 3 | South | 311 | Nsanje | Nsanje | 31101 | Ndamera | Rural |
| 781 | 3 | South | 311 | Nsanje | Nsanje | 31106 | S/C Mbenje | Rural |
| 792 | 3 | South | 311 | Nsanje | Nsanje | 31120 | Nsanje | Urban |
| 804 | 3 | South | 312 | Balaka | Balaka | 31201 | Nsamala | Rural |
| 815 | 3 | South | 312 | Balaka | Balaka | 31204 | Kalemebo | Rural |
| 827 | 3 | South | 313 | Neno | Neno | 31301 | Dambe | Rural |
| 838 | 3 | South | 313 | Neno | Neno | 31303 | Symon | Rural |
| 850 | 3 | South | 313 | Neno | Neno | 31320 | Neno Boma | Urban |

## Annex 1.2: Transmittal form A

HH IDENTIFICATION

CLUSTER (EA) NUMBER CLUSTER (EA) NAME

DHS Supervisor No. MN team lead No: MN enumerator ID

#; DHS HH No (write in from coversheet); Place HH Barcode label here; Field Notes (Record additional respondent information). HH Visit# (check); Eligible PSC; Eligible SAC; Eligible WRA; Eligible Men; Food Sample collection. # in HH; # complete; # in HH; # complete; # in HH; # complete; # in HH; # complete; Salt; Sugar; Oil. 1; 2. 1. 2. 3. 4. 5. 6. 7. 8. 9. 10. 11. 12. 13. 14. 15. 16. 17. 18. 19. 20. 21. 22.

| Result Codes |  |  |
| --- | --- | --- |
| Household Visits | Respondent Questionnaire | Food Collection |
| [1] Eligible participants interviewed [2] Partially completed (at least one incomplete questionnaire/not all members interviewed) [3] HH refused [4] No HH member or adult responded at home during visit [6] HH vacant, moved or destroyed [7] Other | [1] Completed respondent [2] Refused [3] Incomplete [4] Not Available [5] Other | [0] Not collected [1] Collected |

## Annex 1.3: Training Schedule

WEEK 1

|  | Monday Nov 30th | Tuesday December 1st | Wednesday December 2nd | Thursday December 3rd | Friday December 4th | Saturday December 5th |
| --- | --- | --- | --- | --- | --- | --- |
| AM | - Survey Overview - Roles and Responsibilities - Timeline | - Interview skills - Detail questionnaire review (practice) | - Field testing - Hemocue - Anemocheck (including use of tablet) - Malaria - DBS (PSC) - Urine dipstick - RBC lysate (WRA) - Referrals and referral forms | - Labelling (practice) - Field forms - Cluster control - Referrals - Sample tracking | - Review of blood collection Review questionnaires Practice cont. | - Nurses: blood collection practice – Zomba district hospital - Lab techs: review procedures - F&H: food collection practice, review questionnaire, WYD |
| Break |  |  |  |  |  |  |
| Am | - Universal precautions - Cold chain | Review cont…. | - Field testing continued | Labelling and form practice | Anthropometry practice |  |
| Lunch |  |  |  |  |  |  |
| PM | - Household food collection - Setting up the community field lab | - Food collection Testing Labelling - Replacement of foods | - Specimen processing - Centrifugation - Labelling - Storage and cold chain | Full demo and practice. | - Anthropometry standardization | - Team and regional leads: supervisor training |
| Break |  |  |  |  |  |  |
| PM | - Overview of Questionnaire - Labeling overview - DHS handover | - Specimen collection - Venous blood - Urine - Cold chain - Labels MRDR | Cont. | - Anthro - Muac - odema - Standardization | Anthropometry standardization |  |

Training 8am-12, lunch 12-1pm, 1pm-5pm

Time needs to be scheduled for the DHS team leads and MN team leads to have a half-day session on handover

WEEK 2

|  | Monday December 6th | Tuesday December 8th | Wednesday December 9th | Thursday December 10th | Friday December 11th |
| --- | --- | --- | --- | --- | --- |
| AM | - Anthropometry standardization (if needed – if not further review and practice) | - Pilot | Pilot | Field work starts | Field work starts |
| Break |  |  |  |  |  |
| Am |  |  |  |  |  |
| Lunch |  |  |  |  |  |
| PM | - Quiz |  |  |  |  |
| Break |  |  |  |  |  |
| PM | - Preparations for the pilot |  |  |  |  |

## Annex 1.4: Procedures for food collection

# Collection of oil samples

- Prepare an oil sample tube (ensure the tube has a cover) and take out the label for the oil

- Fill the tube at least half full or completely full of oil and tightly seal the tube with the screw cap.

- Stick the label on the oil sample container. (Because labels may come loose, take your scotch tape and over-tape the label on the oil sample container, make a bit more than 1 round, so that the beginning and the end of the tape overlap. This minimizes the risk of losing the label.)

- Cover the oil tube with tin foil to protect it from light and place in a brown paper bag with the cluster number written on it

- Place the oil questionnaire label on the questionnaire

## Collection of salt and sugar samples

Example using sugar

- Prepare a small sachet bag and take out the label for the sugar.

- Fill the small sachet bag with at least 4 tablespoons of sugar and close the bag.

- Stick the label on the sugar bag.

- Place the sugar into a larger paper bag with the cluster number marked on the outside

- Place the sugar questionnaire label on the questionnaire

For all food samples this is the minimum amount that should be gathered in each household:

Minimum sample required for analysis

| Food | Weight (g) | Measure |
| --- | --- | --- |
| Sugar | 44 | 4 table spoons |
| Salt | 22 | 2 table spoons |
| Oil |  | Half the collection tube |

# MODULE 2: INTERVIEWS

## Human Rights and Consent Issues

Before performing any survey, care must be taken to assure and respect the rights of individuals.  In this study, we will take informed consent for all those we interview. You will need to sign the questionnaire to verify that consent has been provided.  The interviewer will explain to the mother/caregiver as per the questionnaire guide, the purpose of the survey, the type of the questions and the requirement to obtain blood specimens.  If the person refuses, his/her wish is accepted.  All results of this study will be confidential and all information will be used for research and public health purposes only.  Immediate feedback to the mother/caregiver is possible for haemoglobin and malaria testing only. Those results will be provided and a referral to the Reference Hospital will be made if the results demonstrate anaemia and/or malaria.

## Interview Techniques

Successful interviewing is an art and should not be treated as a mechanical process. Each interview is a new source of information, so make it interesting and pleasant. The art of interviewing develops with practice but there are certain basic principles that should be followed by every successful interviewer. In this section you will find a number of general guidelines and tips on how to build rapport with a respondent and conduct a successful interview.

The interviewer and the respondent are strangers to each other and one of the main tasks of an interviewer is to establish rapport.  The respondent's first impression of you will influence their willingness to co-operate with the survey. Be sure that your appearance is neat and your manner friendly as you introduce yourself.  Of course, before you start to work in an area, your supervisor will have informed the local leaders, who will in turn, inform the families in the area that you will be coming to interview them.

1.	Make a Good First Impression

When first approaching the respondent, do your best to make her feel at ease.  With a few well-chosen words you can put the respondent in the right frame of mind for the interview.  Open the interview with a smile and greeting and then proceed with your introduction.

2.	Always have a Positive Approach

Never adopt an apologetic manner, and do not use words, as "Are you too busy?” "Would you spare a few minutes?" or "Would you mind answering some questions?" Such questions invite refusal before you start.  Rather, tell the respondent, "I would like to ask you a few questions", or "I would like to talk with you for a few moments".

3.	Stress Confidentiality of Responses when Necessary

If the respondent is hesitant about responding to the interview or asks what the data will be used for, explain that the information you collect will remain confidential, no individual names will be used for any purpose and that all information will be pooled to write a report.  Also, you should never mention other interviews or show completed questionnaires to other interviewers or supervisor in front of a respondent or any other person.

4.	Answer Any Questions from the Respondent Frankly

Before agreeing to be interviewed, the respondent may ask you some questions about the survey or how she was selected to be interviewed.  Be direct and pleasant when you answer.  However, if she asks medical questions, or questions that you cannot answer about the health services, tell her that you will try to answer her questions after you have finished the interview and consult with your supervisor.

The respondent may ask about the length of the interview.  Tell her that the interview usually takes about 40 minutes.

5.	Interview the Respondent Alone

The presence of a third person during an interview can keep you from getting frank, honest answers from a respondent.  It is, therefore, very important that the individual interview be conducted privately and that all questions are answered by the respondent herself. When you are interviewing a person try to stop, politely other members of the house from responding on their behalf.  If you feel that a person in the house is influencing the responses of others, consult with your supervisor and try to interview or distract her/him from the interview that you are conducting.

Sometimes asking for privacy will make others more curious, so they will want to listen; you will have to be creative.  Establishing privacy from the beginning will allow the respondent to be more attentive to your questions.

If it is difficult to interview the person alone, you may have to carry out the interview with the other people present.  However, try to separate yourself and the respondent from the others as much as possible.  And ensure that other people present do not answer or influence the answers of the respondent.

6. Be Neutral throughout the Interview

Most people are polite and will tend to give answers that they think you want to hear.  It is therefore very important that you remain absolutely neutral as you ask the questions.  Never either by the expression on your face or by the tone of your voice, allow the respondent to think that she has given the "right" or "Wrong" answers to the question.  Never appear to approve or disapprove of any of the respondent's replies.

The questions are all carefully worded to be neutral.  They do not suggest that one answer is more likely or preferable to another answer.  If you fail to read the complete question, you may destroy that neutrality.

If the respondent gives an ambiguous answer, try to probe in a neutral way, asking questions such as:

"Can you explain a little more?"

"I did not quite hear you, could you please tell me again?"

"There is no hurry.  Take a moment to think about it"

7.    Never Suggest Answers to the Respondent

If a respondent's answer is not relevant to a question, do not probe her by saying something like "I suppose you mean that ...... Is that right?"  In many cases, she will agree with your interpretation of her answer, even when that is not what she meant.  Rather, you should probe in such a manner that the respondent herself comes up with the relevant answer.  You should never read out the list of coded answers to the respondent, even if she has trouble in answering.

8. Do not Change the Wording or Sequence of Questions

The wording of the questions and their sequence in the questionnaire must be maintained.  If the respondent has misunderstood the question, you should repeat the question slowly and clearly.  If one still does not understand, you may reword the question, being careful not to alter the meaning of the original question.  Provide only the minimum information required to get an appropriate response.

9.	Handle Hesitant Respondents Tactfully

There will be situations where the respondent simply says "I don't know", gives an irrelevant answer, acts very bored or detached, contradicts something she has already said, or refuses to answer the question.  In these cases you must try to re-interest her in the conversation.  For example, if you sense that she is shy or afraid, try to remove her shyness or fear before asking the next question.  Spend a few moments talking about things unrelated to the interview (for example) her town or village, the weather, her daily activities etc.).

If the woman is giving irrelevant or elaborate answers, do not stop her abruptly or rudely, but listen to what she has to say.  Then try to steer her gently back to the original question.  A good atmosphere must be maintained throughout he interview.  The best atmosphere for an interview is one in which the respondent sees the interviewer as a friendly sympathetic and responsive person who does not intimidate her, and to whom she can say anything without feeling shy or embarrassed.  As indicated earlier, the major problem in controlling the interview may be one of privacy.  This problem can be prevented if you are able to obtain a private area in which to conduct the interview.

If the respondent is reluctant or unwilling to answer a question, try to overcome her reluctance, explaining once again that the same question is being asked of women all over the country and that the answers will be merged together.

If she still refuses, simply write REFUSED next to the question and proceed as if nothing had happened.  If you have successfully completed the interview, you may try to obtain the missing information at the end, but do not push too hard for an answer.  Remember, the respondent cannot be forced to give an answer.

10.	Do not Form Expectations

You must not form expectations as to the ability and knowledge of the respondent can influence the interview.  The respondent, believing that you are different from her, may be afraid or mistrustful.  You should always behave and speak in such a way that she is put at ease and is comfortable talking to you.

11.	Do Not Hurry the Interview

Ask the questions slowly to ensure the respondent understands what she is being asked.  After you have asked a question, pause and give her time to think.  If the respondent feels hurried or is not allowed to formulate her own opinion she may respond with "I don't know" or give up the interview, say to the respondent "There is no hurry.  Your opinion is very important so consider your answers carefully".

Summary of good interviewing techniques

Before beginning the interview

1. Put the person at ease

  - Thank them for welcoming you into their home and accepting to participate in the survey.

  - Explain the purpose of the survey: This is survey to help us plan a health and nutrition program for young children in the community

  - Obtain informed consent

  - Tell the person: how long the survey will take; there are no right or wrong answers; all responses are confidential; at end of interview, lab work will be completed.

2. Make a good first impression

  - Smile

  - Be prepared

During the interview

1. Interview the person alone or within the family context to ensure privacy2. Ask the questions as written on the questionnaire

  - Wording and sequence of questions must be maintained

  - Do not rephrase the question

3. Stress confidentiality of responses when necessary

- No individual names will be used

- All information is combined for the report

4. Answer questions from the respondent frankly

- Be direct and pleasant when answering questions

5. Be neutral with your expression and tone of voice

6. Never approve or disapprove of an answer

7. Probe in a neutral way:  Can you explain a little more; I did not hear you, could

you tell me again; There is no hurry, take a moment to think about it.

8. Never suggest answers to the respondent

9. Do not hurry through the interview

10. Ask questions slowly so the so the person understands

11. After asking the question, pause and give the person time to think

12. Feel free to say: “There is no hurry. Your answer is important.”

At the end of the interview

1. Thank the person for answering the questions in the survey

2. Check survey for completeness

3. Pass their questionnaire to the field technician for the next phase of the survey.

Requirements for the completion of the questionnaire

- DO NOT ever falsify information on the questionnaire. The response recorded on the questionnaire has to match the response from the respondent.

- NEVER use pencil to record answers on the interview page. Always use blue pen.

- NEVER recopy questionnaires.

- Always correct mistakes on the questionnaire as taught in the training.

- NEVER record any information about the interview on notebooks. Record ALL information about the interview on the questionnaires you have been provided. Any calculations you make should be written on the back of the questionnaire.

- Anything out of the ordinary should be explained either in the margins or on the back of the page. These comments are very helpful to the supervisor and field editor in checking questionnaires. Comments are also read in the office and used to resolve problems encountered during data entry.

Completion of the Questionnaire

To collect the information, the interviewer must understand how to ask each question and how to correctly record the answers the respondent gives. Also the interviewer must follow the instructions in the questionnaire.

Recording Responses

Interviewers will use pens with blue ink to complete questionnaires.

Writing Numbers

Please always write numbers following the recommended formats below.

For number one, do not record the number slanted or add a hat or a line at the base.

Correct					Not correct

or

For 2 and 3, do not add extra circles or swirls

Correct					Not correct

For number 4, do not close the top of the number to avoid confusion with number 9

Correct					Not correct

For number 5, do not close the left end the number to avoid confusion with number 6

Correct					Not correct

For number 6, do not close the circle too high to avoid confusion with zero

Correct					Not correct

For number 7, make a small dash in the middle of the seven to avoid confusion with 1.

Correct					Not correct

For number 8, make carefully with the two circles touching

Correct

For number 9, close the circle at the top to avoid confusion with number 4.

Correct					Not correct

Correcting Mistakes

It is very important that you record all answers neatly. If you make a mistake, make two diagonal lines over the mistake and then record the correct answer.

Do not erase an answer, use an eraser or use white correction fluid. Just put two lines through the incorrect response.

Here is how to correct a mistake:

Example:

Remember that if you do not cross out mistakes with two lines, it may not be possible to determine which answer is correct during data entry.

## Detailed instructions for questionnaire

It is very important that you ask each question exactly as it is written on the questionnaire (except where indicated by special instructions). If the respondent does not understand the question, you may need to use extra probing questions. Probing questions are included in the questionnaire and are also discussed during interviewer training. It is important that all interviewers use the same probing questions.

In some cases, a respondent may truly not know the answer to a question or refuse to answer a question. However, you must record an answer for all questions that you ask the respondent. Do not leave any questions blank because it may look as though you forgot to ask the question. Some questions have a “don’t know” answer code. You can circle that code if the respondent is unable to remember despite the probing questions. For other questions, there is not a “don’t know” answer code. For these questions, if the respondent truly cannot remember despite your probing, or refuses to answer, you should leave the question blank and write a comment on the questionnaire, in the margin on the right. The margins should also be used to make notes on anything out of the ordinary or any problems you may encounter during the interview.

Throughout the questionnaire, there are statements that appear in italics. These are interviewer instructions, and should not be read aloud to the respondent.

Underlined letters indicate that you should replace the text with information that the respondent has already given you. For example, (NAME) will often appear in underlined font. Here, (NAME) indicates that the text in parentheses needs to be replaced by the name of the child for the module.

Most questions have pre-coded responses. It is important that you do not read these choices aloud. When you ask a question, you should listen to the respondent’s answer, then circle the code next to the pre-coded response that best matches her answer.

Skip patterns

It is very important that you ask the respondent only those questions relevant to her situation. For certain questions, you will skip to the next appropriate question, or end the module, if the respondent gives a particular response.  Skip instructions are usually located in the second to last column in the far right-hand of the questionnaire.

Note on the language to be used for filling the questionnaire.
Answers to all open-ended questions should be written in English. All responses should be written very clearly.

Cover Page:  Consent. You must seek the respondent’s consent for participation in the survey. Read the informed consent statement exactly as it is written. This statement explains the purpose of the survey. It assures the respondent her participation in the survey is completely voluntary and that she can refuse to answer any questions or stop the interview at any point.

After reading the statement, you (not the respondent) must sign in the space provided to affirm that you have read the statement to the respondent.

If the mother/caregiver does not agree to be interviewed, circle ‘4’ on the interview visits module under the section where you record the disposition of visits 1,2 or 3.  Thank the respondent, and end the interview.

Stick the questionnaire label in the space provided on the cover page of the questionnaire.

QUESTIONNAIRE ADMINISTRATION INSTRUCTIONS

This section of the field manual provides detailed instructions for administering the questionnaire. There are five sub-sections, which correspond to the modules of the questionnaire: (1) food fortification, (2) biological information for children age 6 months to 5 years, (3) biological information for children age 6-14 years, (4) biological information for women age 15-49 years, and (5) biological information for men age 20-54 years.

Before beginning each interview, fill out the cover page. All information on the cover page is required.

FOOD FORTIFICATION

The first module focuses on food fortification. In this module, you will ask respondents about the food in their households, observe the food brands, and determine if the foods are fortified with nutrients. Also, you will ask questions about household food security.

| Question number | Questions and filters | Instructions |
| --- | --- | --- |
| 100 | ASK CONSENT FOR FOOD FORTIFICATION COVERAGE INFORMATION FROM HEAD OF HOUSEHOLD/OTHER ADULT. | Read the script provided on the questionnaire exactly as written. When introducing yourself, provide your first name only. For example, “Hello. My name is Ruth.” Be sure to ask, “Do you have any questions?”. Then, pause to give the respondent time to respond. Be patient. It may take the respondent some time to think of questions and ask them. If the respondent has a question, then answer the respondent’s question. Next, finish reading the script to ask permission to conduct the interview. |
| 101 | CIRCLE THE CODE AND SIGN YOUR NAME | If the respondent grants you permission to interview him/her, circle “1” and sign your name. If the respondent refuses to be interviewed, circle “2” and skip to question No. 200. If other, circle “6” and write the reason on the line labelled “SPECIFY”. Then, skip to question No. 200. |
| 102 | Do you have salt in your household today? IF YES: Please can we see the salt you have in the household? | “in your household” means in the place where the respondent lives Explain to the respondent that you are asking whether he/she has salt in the household at the moment. If YES, circle “1”. If NO, circle “2” and skip to question No. 106. If there is more than one type of salt in the household, ask for the one most commonly used. For example, ask “Which type of salt do you use most often?” A respondent may show you salt in a container (such as a bag or bowl) that is not the original container that the salt came in when it was purchased from the store or market. If this happens, ask, “May I see the salt in the original container it came in when you purchased it?” |
| 103 | OBSERVE THE BRAND OF THE SALT RECORD OBSERVATION. | Observe the brand of salt and circle the number that corresponds to the brand. For example, if the brand is BOTSALT, then circle “11”. If the salt is NOT LABELLED, circle “95” and skip to question No. 105. If you observe a brand that is not listed, circle “96” for OTHER and write the name of the brand on the line labelled “SPECIFY”. Do not read the brands aloud to the respondent. |
| 104 | RECORD IF THE SALT IS LABELLED AS IODIZED | Read the label(s) on the container carefully to find out if the salt is iodized/contains iodine. Circle the correct option. If you cannot read the label for any reason (for example, the label was worn off, torn, or damaged by water), then record “8” for DON’T KNOW. |
| 105 | Please may we take a small sample of your salt so that we can test it for iodine? PUT THE SALT SPECIMEN BAR CODE LABEL ON THE SALT CONTAINER AND THE SALT FORM LABEL ON THE FOOD CONTROL FORM [B] | “small” means 2 tablespoons of salt If SALT NOT COLLECTED, circle “9995”. If OTHER, circle “9996” and specify the reason on the line labelled “SPECIFY REASON”. |
| 106 | Do you have any sugar in your household today? IF YES: Please can we see the main type of sugar you have in the household? | “in your household” means in the place where the respondent lives Explain to the respondent that you are asking whether he/she has sugar in the household at the moment. If YES, circle “1”. If NO, circle “2” and skip to question No. 110. If there is more than one type of sugar in the household, ask for the one most commonly used. For example, ask “Which type of sugar do you use most often?” A respondent may show you sugar in a container (such as a bag or bowl) that is not the original container that the sugar came in when it was purchased from the store or market. If this happens, ask, “May I see the sugar in the original container it came in when you purchased it?” |
| 107 | OBSERVE THE BRAND OF THE SUGAR RECORD OBSERVATION. | Observe the brand of sugar. If the brand is ILOVO, circle “11”. Do not read the brand aloud to the respondent. If the sugar is NOT LABELLED, circle “95” and skip to question No. 109. If you observe a brand other than ILOVO, circle “96” for OTHER and write the name of the brand on the line labelled “SPECIFY”. |
| 108 | RECORD IF THE SUGAR IS LABELLED AS FORTIFIED WITH VITAMIN A | Read the label(s) on the container carefully to find out if the sugar contains vitamin A. Circle the correct option. If you cannot read the label for any reason (for example, the label was worn off, torn, or damaged by water), then record “8” for DON’T KNOW. |
| 109 | Please may we take a small sample of your sugar so that we can test it for vitamin A? PUT THE SUGAR SPECIMEN BAR CODE LABEL ON THE SUGAR CONTAINER AND THE SUGAR FORM LABEL ON THE FOOD CONTROL FORM [B] | “small” means 4 tablespoons of sugar . The 4 tablespoons will be put into a small ziplock and labelled. It will then be placed in a brown paper bag to prevent sunlight from affecting it. If SUGAR NOT COLLECTED, circle “9995”. If OTHER, circle “9996” and specify the reason on the line labelled “SPECIFY REASON”. |
| 110 | Do you have any oil in your household today? IF YES: Please can we see the main type of oil you have in the household? | “in your household” means in the place where the respondent lives Explain to the respondent that you are asking whether he/she has oil in the household at the moment. If YES, circle “1”. If NO, circle “2” and skip to question No. 114. If there is more than one type of oil in the household, ask for the one most commonly used. For example, ask “Which type of oil do you use most often?” A respondent may show you oil in a container (such as a bag or bowl) that is not the original container that the oil came in when it was purchased from the store or market. If this happens, ask, “May I see the oil in the original container it came in when you purchased it?” |
| 111 | OBSERVE THE BRAND OF THE OIL RECORD OBSERVATION. | Observe the brand of sugar. For example, if the brand is KAZINGA, circle “11”. If the oil is NOT LABELLED, circle “95” and skip to question No. 113. If you observe a brand that is not listed, circle “96” for OTHER and write the name of the brand on the line labelled “SPECIFY”. Do not read the brands aloud to the respondent. |
| 112 | RECORD IF THE OIL IS LABELLED AS FORTIFIED WITH VITAMIN A | Read the label(s) on the container carefully to find out if the oil contains vitamin A. Circle the correct option. If you cannot read the label for any reason (for example, the label was worn off, torn, or damaged by water), then record “8” for DON’T KNOW. |
| 113 | Please may we take a small sample of your oil so that we can test it for vitamin A? PUT THE OIL SPECIMEN BAR CODE LABEL ON THE OIL TUBE CONTAINER AND THE OIL FORM LABEL ON THE FOOD CONTROL FORM [B] | “small” means about half of the oil collection tube. If OIL NOT COLLECTED, circle “9995”. If OTHER, circle “9996” and specify the reason on the line labelled “SPECIFY REASON”. The tube will be labelled and then wrapped in tinfoil to prevent sunlight from affecting it. |
| 114 | Do you have Blue Band Margarine in your house currently? | “in your house” means in the place where the respondent lives Explain to the respondent that you are asking whether he/she has Blue Band Margarine in the household at the moment. |
| 115 | In the past 7 days, did anyone in your household purchase: - Wheat flour? - Pasta? - Bread? - Spaghetti? - Biscuits? - Mandazi? - Cakes? - Cookies? - Maize flour? | A “household” refers to people who live together in the same dwelling and share meals. Members of a household may include adults and children and people who are not family members, such as domestic workers, lodgers, or friends who live in the household and share food. |
| 116 | In the past 4 weeks (30 days), was there ever no food to eat of any kind in your house because of lack of resources to get food? | Explain to the respondent that you are asking about something that happened over the last 1 month / 30 days. - First, help the person identify an event (maybe holiday or birthday) 1 month / 30 days ago so he/she understands the time frame. No food to eat of any kind in your house because of lack of resources to get food refers to the following: - “Food” means all foods, not just the major staple food whose name is synonymous with “food” in some cultures. - “Lack of resources” refers to the lack of money to buy food or the inability to produce or barter for food. You then will record the number. If the person responds “none”, then record “00”. |
| 117 | How often did this happen in the past 4 weeks (30 days)? | Explain to the respondent that - “RARELY” refers to 1–2 times in the past 4 weeks/30 days - “SOMETIMES” refers to 3–10 times in the past 4 weeks/30 days - “OFTEN” refers to more than 10 times in the past 4 weeks/30 days |
| 118 | In the past 4 weeks (30 days), did you or any household member go to sleep at night hungry because there was not enough food? | This question asks about a situation in which there is no food to eat of any kind in the house because food was not available to household members through usual means (e.g., through purchase or barter, gifts, from the garden or field, from storage structures). |
| 119 | How often did this happen in the past 4 weeks (30 days)? | Explain to the respondent that - “RARELY” refers to 1–2 times in the past 4 weeks/30 days - “SOMETIMES” refers to 3–10 times in the past 4 weeks/30 days - “OFTEN” refers to more than 10 times in the past 4 weeks/30 days |
| 120 | In the past 4 weeks (30 days), did you or any household member go a whole day and night without eating anything at all because there was not enough food? | To “go a whole day and night without eating” - Refers to not eating because there was not enough food. - It does not refer to times when the person chose not to eat for a whole day (for example, when fasting or dieting), for example during Ramadan. “anything at all” means nothing or no food at all |
| 121 | How often did this happen in the past 4 weeks (30 days)? | Explain to the respondent that - “RARELY” refers to 1–2 times in the past 4 weeks/30 days - “SOMETIMES” refers to 3–10 times in the past 4 weeks/30 days - “OFTEN” refers to more than 10 times in the past 4 weeks/30 days |
| 122 | Has your household received coupons for the Farm Input Subsidy Program (FISP) for this season (2015-2016)? | Explain to the participant that coupons are exchanged for fertiliser, maize seeds and legume seeds. “this season” refers to 2015/2016 farming year. If any member of the household is a FISP beneficiary |
| 123 | Does your household participate in the social cash transfer programme? | A “household” refers to people who live together in the same dwelling and share meals. The social cash transfer programme is a programme run by the government that provides cash for school fees and taking care of the home if there is a school going child in the household. |
| 124 | Is your household on the Malawian Vulnerability Assessment Committee (MVAC) list this season (2015-2016)? | A “household” refers to people who live together in the same dwelling and share meals. The Malawian Vulnerability Assessment Committee – assess the situation of the household survivorship in terms of food, cash, welfare, markets. “this season” refers 2015 year, vulnerability assessment of 2014/2015 |
| 125 | Did your household receive food or cash support during last year’s (2014-2015) drought and flood response from the Malawian Vulnerability Assessment Committee (MVAC)? | A “household” refers to people who live together in the same dwelling and share meals. Members of a household may include adults and children and people who are not family members, such as domestic workers, lodgers, or friends who live in the household and share food. Explain to the respondent that if any member of their household received food or cash support, then they should answer “yes”. |
| 126 | RECORD IF REPLACEMENT ITEMS WERE PROVIDED TO HOUSEHOLD | Circle the correct option. Note that if a household provides oil they should be given oil. If they provide all 3 (salt, oil, sugar) they will be given all 3 (salt, oil, sugar). |

BIOLOGICAL INFORMATION FOR CHILDREN AGE 6 MONTHS TO 5 YEARS

This modules involves asking questions about children age 6 months to 5 years and collecting biological information.

| Question number | Question | Instructions |
| --- | --- | --- |
| 200 | - | - |
| 201 | - | - |
| 202 | What is (NAME)’s date of birth? | Explain to the respondent that you would like to know the day, month, and year that (NAME) was born. If they are uncertain ask to see the health card, birth certificate or baptism certificate. |
| 203 | - | - |
| 204 | - | - |
| 205 | - | - |
| 206 | - | - |
| 207 | - | - |
| 208 | - | - |
| 209 | - | - |
| 210A | In the last week, has (NAME OF CHILD) taken iron tablets/syrups/Multiple micronutrient powders? SHOW COMMON IRON TABLETS/SYRUP/MNP IN MALAWI. | Show the respondent the common iron tablets, syrup, and multiple micronutrient powders. |
| 210 | In the last six months, has (NAME OF CHILD) received deworming treatment? | “deworming treatment” refers to any pill(s) that (NAME) has taken to get rid of worms |
| 211 | In the last month, has (NAME OF CHILD) received any therapeutic foods, such as PLUMPY NUT [CHIPONDE]? SHOW SACHET (s). | “therapeutic foods” refers to any specialized foods that (NAME) received to meet his/her nutritional needs Explain to the respondent that PLUMPY NUT [CHIPONDE] is one example of a therapeutic food. There may be other kinds of therapeutic foods that (NAME) received, such as Nutriset F-75 therapeutic milk which comes in an orange package, F-100 therapeutic milk which comes in a blue package, or Likuni (which is a corn soya blend that is also called Super Cereal plus). |
| 212 | In the last month, has (NAME OF CHILD) received a vitamin A capsule? | A “vitamin A capsule” refers to a pill that has vitamin A in it. Show the caregiver the two types of vitamin A. |
| 213 | Has (NAME OF CHILD) had a fever in the last 2 weeks? | Explain to the respondent that you are asking about something that happened over the last 14 days. |
| 214 | Has (NAME OF CHILD) had a fever in the last 24 hours? | Explain to the respondent that you are asking about something that happened over the last 24 hours. |
| 215 | Has (NAME OF CHILD) had diarrhea in the last 2 weeks? | Explain to the respondent that you are asking about something that happened over the last 14 days. Explain to the respondent that diarrhea is more than 3 loose or watery stools in a 24 hour period. |
| 216 | Has (NAME OF CHILD) had a cough or breathing problems in the last 2 weeks? | Explain to the respondent that you are asking about something that happened over the last 14 days. |
| 217 | Has (NAME OF CHILD) been ill with malaria in the last 2 weeks? | Explain to the respondent that you are asking about something that happened over the last 14 days. |
| 218 | Have you noticed blood in (NAME OF CHILD)’s urine in the past 2 weeks? | Explain to the respondent that you are asking about something that happened over the last 14 days. |
| 219 | In the last six months, has (NAME OF CHILD) received a blood transfusion? | Ask if the child had been taken or referred to a health facility for a blood transfusion in the last 6 months. Use a seasonal event or time of year with the caregiver and ask if the child had been given a transfusion between that time and now |
| 220 | At what time approximately did (NAME OF CHILD) eat her/his most recent meal or was breastfed? | “eat her/his most recent meal” refers to the last meal (NAME) had today. Remember that breastmilk counts as a meal. Explain to the respondent that you would like to know the time, such as 11:30. When recording the response, use a 24 hour clock. |
| 221 | - | - |
| 222 | - | - |
| 223 | - | - |
| 224 | - | - |
| 225 | - | - |
| 226 | - | - |
| 227 | - | - |
| 228 | - | - |
| 229 | - | - |
| 230 | - | - |
| 231 | - | - |
| 232 | - | - |
| 233 | - | - |
| 234 | - | - |
| 235 | - | - |
| 236 | - | - |
| 237 | - | - |
| 238 | - | - |
| 239 | In order to determine if your child has blood in their urine, which might suggest that they have schistosomiasis, we would like to collect a urine sample from your child. If you can provide this now, we appreciate it. If not now, we can come back to pick up the sample at a later time. INSTRUCTIONS IF UNABLE TO PRODUCE AT WILL: FOR URINE: We will return tomorrow to pick up your child’s urine. We would like the freshest urine you can give us. Please use this cup to collect your child’s urine. | If the child cannot provide urine and you need to come back to pick up the sample at a later time, mark the child’s bracelet with a marker and mark the cup for the child’s urine with the same marker. For example, draw a small circle on the child’s bracelet with a green marker and draw a small circle on the cup for the child’s urine with the same green marker. Note that the purpose of marking the bracelet and cup with the same color is so that the colors will match up and you will know which cup corresponds to which person. If you will be returning to pick up urine from more than one person, make sure that you use different colors to mark each person’s bracelet and his/her cup. For example, use a blue marker to mark a second child’s bracelet and cup, and use a red marker to mark a woman’s bracelet and cup. |
| 240 | - | - |
| 241 | - | - |
| 242 | - | - |
| 243 | - | - |
| 244 | - | - |
| 245 | - | - |
| 246 | - | - |
| 247 | - | - |
| 248 | - | - |
| 249 | - | - |
| 250 | - | - |
| 251 | - | - |
| 252 | - | - |
| 253 | - | - |

BIOLOGICAL INFORMATION FOR CHILDREN AGE 6-14 YEARS

This modules involves asking questions about children age 6 months to 14 years and collecting biological information.

| Question number | Question | Instructions |
| --- | --- | --- |
| 300 | - | - |
| 301 | - | - |
| 302 | What is (NAME)’s date of birth? | Explain to the respondent that you would like to know the day, month, and year that (NAME) was born |
| 303 | - | - |
| 304 | - | - |
| 305 | - | - |
| 306 | - | - |
| 307 | - | - |
| 308 | - | - |
| 309A | In the last week, has (NAME OF CHILD) taken iron tablets or syrups? SHOW COMMON IRON TABLETS IN MALAWI. | Show the respondent common iron tablets in Malawi. |
| 309 | In the last six months, has (NAME OF CHILD) received deworming treatment? | “deworming treatment” refers to any pill(s) that (NAME) has taken to get rid of worms |
| 310 | In the last month, has (NAME OF CHILD) received any therapeutic foods, such as PLUMPY NUT? SHOW SACHET. | “therapeutic foods” refers to any specialized foods that (NAME) received to meet his/her nutritional needs Explain to the respondent that PLUMPY NUT [CHIPONDE] is one example of a therapeutic food. There may be other kinds of therapeutic foods that (NAME) received. |
| 311 | In the last month, has (NAME OF CHILD) received a vitamin A capsule? | A “vitamin A capsule” refers to a pill that has vitamin A in it |
| 312 | Has (NAME OF CHLD) had a fever in the last 2 weeks? | Explain to the respondent that you are asking about something that happened over the last 14 days. |
| 313 | Has (NAME OF CHILD) had a fever in the last 24 hours? | Explain to the respondent that you are asking about something that happened over the last 24 hours. |
| 314 | Has (NAME OF CHILD) had diarrhea in the last 2 weeks? | Explain to the respondent that you are asking about something that happened over the last 14 days. Explain to the respondent that diarrhea is more than 3 loose or watery stools in a 24 hour period. |
| 315 | Has (NAME OF CHILD) had a cough or breathing problems in the last 2 weeks? | Explain to the respondent that you are asking about something that happened over the last 14 days. |
| 316 | Has (NAME OF CHILD) been ill with malaria in the last 2 weeks? | Explain to the respondent that you are asking about something that happened over the last 14 days. |
| 317 | Have you noticed blood in (NAME OF CHILD)’s urine in the past 2 weeks? | Explain to the respondent that you are asking about something that happened over the last 14 days. |
| 318 | In the last six months, has (NAME OF CHILD) received a blood transfusion? | Ask if the child had been taken or referred to a health facility for a blood transfusion in the last 6 months. Use a seasonal event or time of year with the caregiver and ask if the child had been given a transfusion between that time and now |
| 319 | At what time approximately did (NAME OF CHILD) eat her/his most recent meal? | “eat her/his most recent meal” refers to the last meal (NAME) had today Explain to the respondent that you would like to know the time, such as 11:30. When recording the response, use a 24 hour clock. |
| 320 | - | - |
| 321 | - | - |
| 322 | - | - |
| 323 | - | - |
| 324 | - | - |
| 325 | - | - |
| 326 | - | - |
| 327 | - | - |
| 328 | - | - |
| 329 | - | - |
| 330 | - | - |
| 331 | - | - |
| 332 | - | - |
| 333 | - | - |
| 334 | - | - |
| 335 | - | - |
| 336 | - | - |
| 337 | In order to determine if your child has blood in their urine, which might suggest that they have schistosomiasis, we would like to collect a urine sample from your child. If you can provide this now, we appreciate it. If not now, we can come back to pick up the sample at a later time. INSTRUCTIONS IF UNABLE TO PRODUCE AT WILL: FOR URINE: We will return tomorrow to pick up your child’s urine. We would like the freshest urine you can give us. Please use this cup to collect your child’s urine. | If the child cannot provide urine and you need to come back to pick up the sample at a later time, mark the child’s bracelet with a marker and mark the cup for the child’s urine with the same marker. For example, draw a small circle on the child’s bracelet with a green marker and draw a small circle on the cup for the child’s urine with the same green marker. Note that the purpose of marking the bracelet and cup with the same color is so that the colors will match up and you will know which cup corresponds to which person. If you will be returning to pick up urine from more than one person, make sure that you use different colors to mark each person’s bracelet and his/her cup. For example, use a blue marker to mark a second child’s bracelet and cup, and use a red marker to mark a woman’s bracelet and cup. |
| 338 | - | - |
| 339 | - | - |
| 340 | - | - |
| 341 | - | - |
| 342 | - | - |
| 343 | - | - |
| 344 | - | - |
| 345 | - | - |
| 346 | - | - |
| 347 | - | - |
| 348 | - | - |
| 349 | - | - |
| 350 | - | - |
| 351 | - | - |

BIOLOGICAL INFORMATION FOR WOMEN AGE 15-49 YEARS

For this module, interview women age 15 to 49 years and collect biological information.

| Question number | Question | Instructions |
| --- | --- | --- |
| 400 | - | - |
| 401 | - | - |
| 402 | - | - |
| 403 | - | - |
| 404 | - | - |
| 405 | - | - |
| 406 | - | - |
| 407 | - | - |
| 408 | - | - |
| 409 | - | - |
| 410 | - | - |
| 411 | - | - |
| 412 | - | - |
| 413 | - | - |
| 414 | In the last week, have you taken iron tablets or iron syrup? SHOW COMMON IRON TABLETS IN MALAWI. | Show the respondent iron tablets. |
| 415 | In the last week, have you taken any other kind of vitamin or mineral tablet/syrup/powder? | Explain to the respondent that you would like to know if she has taken any kind of vitamin or mineral tablet/syrup/powder other than an iron tablet or iron syrup. |
| 416 | Have you had a fever in the last 2 weeks? | Explain to the respondent that you are asking about something that happened over the last 14 days. |
| 417 | Have you had a fever in the last 24 hours? | Explain to the respondent that you are asking about something that happened over the last 24 hours. |
| 418 | Have you had a cough or breathing problems in the last 2 weeks? | Explain to the respondent that you are asking about something that happened over the last 14 days. |
| 419 | Have you had diarrhea in the last 2 weeks? | Explain to the respondent that you are asking about something that happened over the last 14 days. Explain to the respondent that diarrhea is more than 3 loose or watery stools in a 24 hour period. |
| 420 | Have you been ill with malaria in the last 2 weeks? | Explain to the respondent that you are asking about something that happened over the last 14 days. |
| 421 | In the past 2 weeks did you notice blood, other than menstrual blood, in your urine? | Explain to the respondent that you are asking about something that happened over the last 14 days. |
| 422 | In the last six months, have you received a blood transfusion? | Ask if the respondent has been taken or referred to a health facility for a blood transfusion in the last 6 months. Use a seasonal event or time of year and ask if the respondent had been given a transfusion between that time and now |
| 423 | Are you pregnant? |  |
| 424 | At what time approximately did you eat your most recent meal? | “most recent meal” refers to the last meal you had today Explain to the respondent that you would like to know the time, such as 11:30 When recording the response, use a 24 hour clock. |
| 425 | - | - |
| 426 | - | - |
| 427 | - | - |
| 428 | - | - |
| 429 | - | - |
| 430 | - | - |
| 431 | - | - |
| 432 | - | - |
| 433 | - | - |
| 434 | - | - |
| 435 | - | - |
| 436 | - | - |
| 437 | - | - |
| 438 | - | - |
| 439 | - | - |
| 440 | - | - |
| 441 | - | - |
| 442 | In order to determine if you have blood in your urine, which might suggest that you have schistosomiasis, we would like to collect a urine sample from you. If you can provide this now, we appreciate it. If not now, we can come back to pick up the sample at a later time. INSTRUCTIONS IF UNABLE TO PRODUCE AT WILL: FOR URINE: We will return tomorrow to pick up your urine. We would like the freshest urine you can give us. Please use this cup to collect your urine | If the respondent cannot provide urine and you need to come back to pick up the sample at a later time, mark the respondent’s bracelet with a marker and mark the cup for the respondent’s urine with the same marker. For example, draw a small circle on the respondent’s bracelet with a green marker and draw a small circle on the cup for the respondent’s urine with the same green marker. Note that the purpose of marking the bracelet and cup with the same color is so that the colors will match up and you will know which cup corresponds to which person. If you will be returning to pick up urine from more than one person, make sure that you use different colors to mark each person’s bracelet and his/her cup. For example, use a blue marker to mark a child’s bracelet and cup, and use a red marker to mark a second woman’s bracelet and cup. |
| 443 | - | - |
| 444 | - | - |
| 445 | - | - |
| 446 | - | - |
| 447 | - | - |
| 448 | - | - |
| 449 | - | - |
| 450 | - | - |
| 451 | - | - |
| 452 | - | - |
| 453 | - | - |
| 454 | - | - |
| 455 | - | - |
| 456 | - | - |
| 457 | - | - |

BIOLOGICAL INFORMATION FOR MEN AGE 20-54 YEARS

For this module, interview men age 20 to 54 years and collect biological information.

| Question number | Question | Instructions |
| --- | --- | --- |
| 500 | - | - |
| 501 | - | - |
| 502 | - | - |
| 503 | - | - |
| 504 | - | - |
| 505 | - | - |
| 506 | In the last week, have you taken iron tablets or iron syrup? SHOW COMMON IRON TABLETS IN MALAWI | Show the respondent common iron tablets. |
| 506A | In the last week, have you taken any other kind of vitamin or mineral tablet/syrup/powder? | Explain to the respondent that you would like to know if he has taken any kind of vitamin or mineral tablet/syrup/powder other than an iron tablet or iron syrup. |
| 507 | Have you had a fever in the last 2 weeks? | Explain to the respondent that you are asking about something that happened over the last 14 days. |
| 508 | Have you had a fever in the last 24 hours? | Explain to the respondent that you are asking about something that happened over the last 24 hours. |
| 509 | Have you had a cough or breathing problem in the last 2 weeks? | Explain to the respondent that you are asking about something that happened over the last 14 days. |
| 510 | Have you had diarrhea in the last 2 weeks? | Explain to the respondent that you are asking about something that happened over the last 14 days. Explain to the respondent that diarrhea is more than 3 loose or watery stools in a 24 hour period. |
| 511 | Have you been ill with malaria in the last 2 weeks? | Explain to the respondent that you are asking about something that happened over the last 14 days. |
| 512 | In the past 2 weeks did you notice blood in your urine? | Explain to the respondent that you are asking about something that happened over the last 14 days. |
| 513 | In the last six months, have you received a blood transfusion? | Ask if the respondent has been taken or referred to a health facility for a blood transfusion in the last 6 months. Use a seasonal event or time of year and ask if the respondent had been given a transfusion between that time and now |
| 514 | At what time approximately did you eat your most recent meal? | “most recent meal” refers to the last meal you had today Explain to the respondent that you would like to know the time, such as 11:30. When recording the response, use a 24 hour clock. |
| 515 | - | - |
| 516 | - | - |
| 517 | - | - |
| 518 | - | - |
| 519 | - | - |
| 520 | - | - |
| 521 | - | - |
| 522 | - | - |
| 523 | - | - |
| 534 | - | - |
| 525 | - | - |
| 526 | - | - |
| 527 | - | - |
| 528 | - | - |
| 529 | - | - |
| 530 | - | - |
| 531 | In order to determine if you have blood in your urine, which might suggest that you have schistosomiasis, we would like to collect a urine sample from you. If you can provide this now, we appreciate it. If not now, we can come back to pick up the sample at a later time. INSTRUCTIONS IF UNABLE TO PRODUCE AT WILL: FOR URINE: We will return tomorrow to pick up your urine. We would like the freshest urine you can give us. Please use this cup to collect your urine | If the respondent cannot provide urine and you need to come back to pick up the sample at a later time, mark the respondent’s bracelet with a marker and mark the cup for the respondent’s urine with the same marker. For example, draw a small circle on the respondent’s bracelet with a green marker and draw a small circle on the cup for the respondent’s urine with the same green marker. Note that the purpose of marking the bracelet and cup with the same color is so that the colors will match up and you will know which cup corresponds to which person. If you will be returning to pick up urine from more than one person, make sure that you use different colors to mark each person’s bracelet and his/her cup. For example, use a blue marker to mark a child’s bracelet and cup, and use a red marker to mark a second man’s bracelet and cup. |
| 532 | - | - |
| 533 | - | - |
| 534 | - | - |
| 535 | - | - |
| 536 | - | - |
| 537 | - | - |
| 538 | - | - |
| 539 | - | - |

# MODULE 3: Anthropometry

The interviewer will be the anthropometrist and the field technician will be the anthropometry assistant

# Measuring children under 24 months of age

Measuring the Child’s Length (if under 24 months of age or 85 cm):

      - Place the measuring board on a hard, flat surface, usually the floor.  If you place the measuring board on a table or other elevated surface, be sure you watch the child carefully so that he does not fall off.

      - Ask the child’s caregiver to remove child’s shoes and head / hair articles.

      - The assistant should kneel at the head end of the board in order to stabilize the head.

      - The measurer should kneel with both knees on the child's right side so that he can hold the head piece with his right hand.

      - With the assistance of the mother, the child should be placed on his back on the board so that the head is against the fixed foot board and the feet are at the open end of the board.  The child's body should be straight and centered on the board.

      - The mother should be on the child's left side to comfort and reassure the child.

      - The measurer places the child’s feet flat together against the foot board, while making sure the child’s legs are straight and the heels and calves are against the board.

      - The assistant ensures that the top of the child’s head is in contact with the foot piece and that the child’s face is looking straight upward (perpendicular to the ground).

      - The measurer gently pushes the head piece against the feet and calls out the measurement to the nearest .1 cm.

      - The child should be released immediately after the measurement is called out.  The measurer and the assistant can help the child rise or hand the child to the mother.

Measuring the Child’s Weight (digital scales)

- Place the digital scale on the ground in as flat and horizontal a spot as possible. Check to see if the scale is placed flat by trying to jiggle it, it should be firmly placed with all four feet in contact with the ground.

- Switch the scale on by passing one’s hand an inch over the surface of the solar detector.

- Wait for the appearance of the zero.

- Test the weight of the standard – if it is correct, then the scale is placed flat and is reading correctly. If not, move it and go through steps 1, 2 and 3 again.

- After standardising the scale to the weight, weigh the child by one of the two following methods:

  - If the child is older and can stand quietly on the scale, place the child standing on the scale. Ensure that the child is balanced and is not being pressed down or held up by another adult. The child should not be touching anything during the weighing, or:

  - If the child cannot stand or will not hold still while on the scale, place the mother on the scale.  Wait until a weight reading appears, then while instructing the mother not to move, pass your hand over the solar detector.  The scale should read "0."  The mother must remain quietly on the scale throughout the procedure.  Hand the child to the mother. Be sure neither the child nor the mother are touching anything.  Wait until another reading appears on the scale; this will be the child's weight.

- Record the weight as shown on the scale on the child's data collection form.

## Tips for successful measurements

Child’s length

Use the correct head and hand position

Correct position

Incorrect position		                          Incorrect position

Assistants  position

Feet flat, heels against the board

Incorrect position

Useful tips for anthropometrists

- Work with your assistant (interviewer). They have been trained to help you. Use the assistant for every measurement. If possible ask the child’s mother to try and distract the child a little so that you can work quickly and take a good measurement.

- Look for the best place to position the anthropometric equipment as soon as you enter the house.  The best place may be outside if the weather permits.  Be sure there is enough light to read the height board and scale and operate the solar detector on the UniScale.

- Do not weight and measure children until the interview is completed for every household member.  Weighing and measuring too early would be considered an intrusion and may distract the respondent during an interview.

- Control the child during all phases of weighing and measuring.  Although some children may object and struggle, the best thing you can do for the child and mother is to complete the weighing and measuring quickly by gently but firmly putting the child in the appropriate positions for measurements.  It may be necessary to have the mother calm the child before continuing.

- Help to minimize the child’s stress by;

  - Talking to them

  - Keeping contact with the child

  - Being firm but gentle

  - Work quickly

  - Remove clothes just before making the measurements, so the child doesn’t get cold

- Record measurements carefully every time.

- Follow every step of the procedure the same way every time. Do not take the procedures for granted; they may seem simple and repetitious, but errors can easily be made which invalidate anthropometric data.

Measuring the Child’s Height (if 24 months or greater or ≥ 85 cm)

- Place the measuring board on a hard flat surface against a wall, table, tree, staircase, or other immovable vertical surface.

- Ask the child’s caregiver to remove child’s shoes and hair articles and then bring the child to the measuring board.

- The assistant kneels on the child's right side.

- The measurer kneels on one knee on child’s left side.

- Place the child’s feet flat together against the centre of the base board. Make sure the child’s legs are straight and the heels and calves are against the board. The child's body should be in the centre of the board.  The assistant can place his right hand on the child's shins and the left hand on the child's knees.

- Make sure that the child’s face is looking straightforward (parallel to the ground). Make sure that the child’s shoulders are level, hands are at the side, and head, shoulders, buttocks and heels are against the board.

- The measurer can now place the headpiece against the board and lower it to the top of the child’s head (flatten hair to head) using her right hand.

- The measurer calls out the measurement to the nearest 0.1 cm.

- The assistant calls back the measurement for confirmation and immediately records the measurement on the questionnaire.

Measuring the Child’s Weight (digital scales)

- Place the digital scale on the ground in as flat and horizontal a spot as possible.  Check to see if the scale is placed flat by trying to jiggle it, it should be firmly placed with all four feet in contact with the ground.

- Switch the scale on by passing one’s hand an inch over the surface of the solar detector.

- Wait for the appearance of the zero.

- Test the weight of the standard – if it is correct, then the scale is placed flat and is reading correctly. If not, move it and go through steps 1, 2 and 3.

- After standardising the scale to the weight, weigh the child by one of the two following methods:

  - If the child is older and can stand quietly on the scale, place the child standing on the scale. Ensure that the child is balanced and is not being pressed down or held up by another adult. The child should not be touching anything during the weighing, or:

  - If the child cannot stand or will not hold still while on the scale, place the mother on the scale.  Wait until a weight reading appears, then while instructing the mother not to move, pass your hand over the solar detector.  The scale should read "0."  The mother must remain quietly on the scale throughout the procedure.  Hand the child to the mother. Be sure neither the child nor the mother is touching anything.  Wait until another reading appears on the scale; this will be the child's weight.

- Record the weight as shown on the scale on the child's data collection form.

Measuring an adult’s weight

- Place the digital scale on the ground in as flat and horizontal a spot as possible.  Check to see if the scale is placed flat by trying to jiggle it, it should be firmly placed.

- Switch the scale on by passing one’s hand an inch over the surface of the solar detector.

- Wait for the appearance of the zero.

- Test the weight of the standard – if it is correct, then the scale is placed flat and is reading correctly. If not, move it and go through steps 1, 2 and 3.

- After standardising the scale to the weight, ask the adult to stand on the scale. Ensure that they are standing quietly and not touching anything. Wait for the weight reading to appear. Record the weight on the data collection form.

Measuring an adult’s height:

- Place the measuring board on the ground against a wall, table, tree, staircase, or other immovable vertical surface.  Make sure it is stable.

- Ask the person to remove their shoes and head / hair articles.

- Ask the person to place their feet together and against the centre of the base board with their back to the board.

- Make sure the person’s legs are straight and the heels and calves are against the board.

- Make sure that the person’s face is looking straightforward (parallel to the ground). Make sure that the shoulders are level, hands are at the side, and head, shoulders, buttocks and heels are against the board.

- Lower the headpiece to the top of the head (flatten hair to head),

- Record the measurement to the nearest .1 cm.

- The assistant calls back the measurement for confirmation and immediately records the measurement on the questionnaire.

MID-UPPER ARM CIRCUMFERENCE IN CENTIMETERS

The mid-upper arm circumference measurement is an indicator of body mass, and is used to identify protein-energy malnutrition.

- Have the mother remove any clothing that covers the left arm.

- Calculate the midpoint of the upper left arm by locating the tip of the shoulders with your fingertips. Bend the woman’s arm to make a right angle. Place a string on the tip of the shoulder and pull it past the tip of the elbow. Note the length of the string which covers the distance between the tip of the shoulder and the tip of the elbow.

- Divide the string in half to find the midpoint of the arm and then mark the midpoint on the arm with a pen.

- Straighten the woman’s arm and wrap the MUAC measuring tape around the arm at the midpoint (ensuring that the numbers are right side up). Make sure the tape is neither too tight nor too loose.

- Record the measurement to the nearest 0.1 cm.

PRESENCE OF BILATERAL OEDEMA (preschool children only)

Oedema is the retention of water in the tissues of the body. Oedema is an indicator of severe acute malnutrition (Kwashiorkor) and warrants immediate referral to a feeding center. To diagnose oedema, moderate finger pressure is applied just above the ankle on the inside of the leg were the shin bone is below the skin, or on the tops of the feet (see figure below). The pressure is kept for about three seconds. (If you count “one thousand and one, one thousand and two, one thousand and three” in English, pronouncing the words carefully, this takes about three seconds.) If there is oedema, an impression remains for some time (at least a few seconds) where the oedema fluid has been pressed out of the tissue. The child should only be recorded as oedematous if both feet clearly have oedema.

It can be quite painful if the enumerator presses hard on the skin. Hard pressure is not required to test for oedema. The team should practice on each other and if anyone finds it painful or uncomfortable then the team member is pressing excessively.

Presence of oedema should be marked on the questionnaire as YES (both legs are positive) or NO (one or no legs are positive).

Useful tips

- Work with your assistant. They have been trained to help you. Use the assistant for every measurement. If possible ask the child’s mother to try and distract the child a little so that you can work quickly and take a good measurement.

- Look for the best place to position the anthropometric equipment as soon as you enter the house.  The best place may be outside if the weather permits.  Be sure there is enough light to read the height board and scale and operate the solar detector on the UniScale.

- Determine the child’s age before beginning measurements. Remember that age determines whether the child is measured lying down or standing up.

- Do not weight and measure children or adults until the interview is completed for every household member.  Weighing and measuring too early would be considered an intrusion and may distract the respondent during an interview.

- Weigh and measure only ONE child at a time. Measure height and weight for child 1, then move on to child 2, 3 etc…  This will avoid recording a child's measurement on the wrong data collection form.

- Control the child during all phases of weighing and measuring.  Although some children may object and struggle, the best thing you can do for the child and mother is to complete the weighing and measuring quickly by gently but firmly putting the child in the appropriate positions for measurements.  It may be necessary to have the mother calm the child before continuing.

- Help to minimize the child’s stress by;

  - Talking to them

  - Keeping contact with the child

  - Being firm but gentle

  - Work quickly

  - Remove clothes just before making the measurements, so the child doesn’t get cold

- Record measurements carefully every time.

- Follow every step of the procedure the same way every time. Do not take the procedures for granted; they may seem simple and repetitious, but errors can easily be made which invalidate anthropometric data.

# MODULE 4: Data Management

## TOOLS:

To achieve these goals, there are a number of tools that we will use to ensure accountability of all team members.

- Team leads reports:

  - Reporting frequency = daily

  - Reporting format = SMS message

  - At the end of every working field day, each MNS team lead will send a concise SMS message to the MNS supervisor. Details of the text will follow, but it will describe the number of participants sampled on a daily basis.

- Supervisor reports:

  - Reporting frequency = weekly

  - Reporting format = Google docs

  - The MNS supervisor will receive text messages daily from each MNS team leads. Data from these text messages will be complied in order to consolidate weekly field activity.

- Lab coordinator reports:

  - Reporting frequency = ongoing

  - format = spreadsheet on Google docs

  - This spreadsheet will be populated as regional labs receive freezer boxes of specimens

## DATA QUALITY PROTOCOL:

- Data quality in the field:

  - Primarily, it is the job of the enumerator, nurse and lab technician to enter legible information into the questionnaire booklets for each participant.

  - The team lead (or if fully occupied then the regional coordinator) will need to look over all data on the booklets to ensure that it can be easily understood. Ultimately, the regional coordinator will be responsible for the data completeness and edits for each team that they oversee.

  - The following tasks are required from the team lead (or regional coordinator):

    - Edit all completed questionnaires in the field.  The supervisor may need to assist the field editor in performing this task since all editing must be completed prior to leaving the cluster

    - Put completed questionnaires from a cluster in order and pack them to be sent to the central office.

### EDITING IN THE FIELD:

*ALWAYS USE A RED PEN TO MAKE CORRECTIONS*

- As you go through the booklets, if a response is missing (that is, there is no answer recorded because the question was not asked) or the response is inconsistent with other information in the questionnaire and you cannot determine the correct response, put a question mark (‘?’) next to the item with a red pen.

- Write the page number or the question number on the front or back of the questionnaire; this way, you can quickly remember later what problems you found. When you have completed the editing, discuss with the enumerator, nurse, or lab technician, individually, the observations you found. Any errors that you find frequently should be discussed with the whole team.

  - If the problems are major, such as discrepancies in the birth history or the health sections, it will be necessary to go back to interview the respondent again or check the forms B and C as the missing data might be recorded on these forms.  If a return visit is not possible, try to establish, with the interviewer’s assistance, the correct response from other information in the questionnaire. For example, if there is no code circled to indicate a person’s sex, you might be able, with the interviewer’s help, to determine from the name which sex the person is.

*UNDER NO CIRCUMSTANCES SHOULD YOU MAKE UP AN ANSWER*

- If it is not possible to return to the household to resolve inconsistencies or missing information, then leave the items as they are. Do not try to fill in every question or to make the questionnaire consistent.

- In checking through each booklet, be sure that the numbers entered in boxes are readable and that the circles used by the interviewer to select the pre-coded options are clearly marked.

- In checking each booklet, make certain that the respondent was asked all questions appropriate for him/her (check that the interviewer followed the skip instructions).

- Check the ranges for all variables that are not pre-coded (e.g., a woman cannot have 24 sons living with her).  Mark any inconsistencies with a red pen.

- The field edits will need to be done by the team lead and the regional coordinator in an ongoing fashion to catch any errors quickly. We do not have flexibility in our schedules to return for re-interviews in most cases. It will be important to identify common errors early on and inform the team to prevent repetitive mistakes.

- Key data pieces to look for:

  - Check that the household identification information has been completed correctly.

  - Check that the informed consent statement has been signed by the interviewer.

- Data quality at the stage of entry (see below in DATA ENTRY GUIDANCE SECTION)

## DATA TRACKING PROTOCOL:

There are two data tracking sheets, which will be active in the field. The next level of data tracking will be at the laboratory (for specimens) and at the NSO office (for data entry of the booklets).

### TRACKING IN THE FIELD:

The two data tracking sheets actively used in the field are for booklets and specimens. THEY WILL LOOK THE SAME (Appendix A). There is a data tracking sheet that will accompany the booklets and the freezer boxes to ensure that samples do not go missing and are handled properly.

EXAMPLE: MNS team #5 finalized cluster 67. On the second (and last) day in the cluster (October 20, 2015, the booklets (21 total) were collected by the regional coordinator. Fourteen freezer boxes of specimens were transported to the regional lab.

| Name (receiving data) | Date received | Cluster # | Booklet or Specimen – specify one | Quantity (number of booklet or freezer boxes) |
| --- | --- | --- | --- | --- |
| Team lead | 20 OCT 2015 | 67 | Booklet | 21 |
| Regional coordinator | 20 OCT 2015 | 67 | Booklet | 21 |

| Name (receiving data) | Date received | Cluster # | Booklet or Specimen – specify one | Quantity (number of booklet or freezer boxes) |
| --- | --- | --- | --- | --- |
| Team lead | 20 OCT 2015 | 67 | Specimen | 14 |
| Regional coordinator | 20 OCT 2015 | 67 | Specimen | 14 |
| Data manager | 21 OCT 2015 | 67 | Specimen | 14 |

### TEAM LEAD REPORTS

- Team leads will report the following information via SMS to the survey coordinator at the end of each field day:

  - Cluster-day

  - Total # household (HH) visited in that cluster (will include all days, if it is day two, then you add together households visited on day 1 and day 2. Do not include refusals in this number)

    - Total number of refusal HH in that cluster

  - # specimens collected per target group that day

EXAMPLE: MNS team #5 visits cluster 67. It is their second day in the cluster and they visited 11 HH yesterday and 10 HH today. There was 1 HH that was a refusal on the second day. For specimen collection on the second day, 15 PSC, 8 SAC, 9 WRA and 4 men.

REPORT FORMAT:

C67-D2. 10 HH. 1R. 15PSC. 8SAC. 9WRA. 4M.

### SUPERVISOR REPORTS

The MNS supervisor will compile information on a weekly basis from the team leads, the lab coordinator and the data manager. These supervisor reports will be shared with the CDC team based in Atlanta. If the MNS supervisor is unable to complete reports independently, Stella Fagbemi (part of the technical support team from CDC) will be notified to assist.

The supervisor report template is a google document to allow for space to add comments and not be constrained by space to share field experiences that may be valuable later on as we reflect back on the survey and the data. For example, if there are unforeseen problems or extreme weather events that may impact the efficiency of the survey, please note them in the comments section.

The reporting frequency is weekly and the format is electronic, so they can be emailed conveniently to Anne Williams (anne.williams@emory.edu) from Stella (sfagbem@emory.edu) and Eunice (elcnyirenda@yahoo.com).

DHS progress report (if necessary).

To be compiled on a weekly basis by the survey coordinator and shared with the CDC team for monitoring and planning purposes, if the MDHS teams get off schedule only.

EXAMPLE: During week of October 5 – 10, the DHS was active in all 3 regions, in 10 districts and each of the 37 teams are accounted for in this report, which was compiled on Oct 12, 2015

| Date of report (preferably on a Monday) | DHS clusters completed in past week | List regions (1,2,3, or ALL) | List districts (27 total – list them) | Comments |
| --- | --- | --- | --- | --- |
| EXAMPLE 10/12/2015 | 40 | ALL | 101, 102, 210, 211, 312, 313 | 36 teams working fine. 1 team delayed due to transportation issues. |
| 11/2/2015 |  |  |  |  |

## Appendix A. Data tracking sheet

Instructions: As data is handed one team member to the next, they will sign for receipt and the data tracking sheet will move with the data from the point of collection to the point of entry (booklet) or storage (specimen)

| Name (receiving data) | Date received | Cluster # | Booklet or Specimen – specify one | Quantity (number of booklet or freezer boxes) |
| --- | --- | --- | --- | --- |

Anticipated flow of Questionnaire Booklets:

Anticipated flow of freezer boxes within cold chain:

Appendix B. Supervisor Report Template

Week of: (enter dates)

Page 1

| MNS team |  | 1 | 2 | 3 | 4 | 5 |
| --- | --- | --- | --- | --- | --- | --- |
| Date (write in date) | Cluster # |  |  |  |  |  |
|  | Households |  |  |  |  |  |
|  | Refusals |  |  |  |  |  |
|  | PSC |  |  |  |  |  |
|  | SAC |  |  |  |  |  |
|  | WRA |  |  |  |  |  |
|  | Men |  |  |  |  |  |
| Date (write in date) | Cluster # |  |  |  |  |  |
|  | Households |  |  |  |  |  |
|  | Refusals |  |  |  |  |  |
|  | PSC |  |  |  |  |  |
|  | SAC |  |  |  |  |  |
|  | WRA |  |  |  |  |  |
|  | Men |  |  |  |  |  |
| Date (write in date) | Cluster # |  |  |  |  |  |
|  | Households |  |  |  |  |  |
|  | Refusals |  |  |  |  |  |
|  | PSC |  |  |  |  |  |
|  | SAC |  |  |  |  |  |
|  | WRA |  |  |  |  |  |
|  | Men |  |  |  |  |  |

Week of: (enter dates)

Page 2

| MNS team |  | 1 | 2 | 3 | 4 | 5 |
| --- | --- | --- | --- | --- | --- | --- |
| Date (write in date) | Cluster # |  |  |  |  |  |
|  | Households |  |  |  |  |  |
|  | Refusals |  |  |  |  |  |
|  | PSC |  |  |  |  |  |
|  | SAC |  |  |  |  |  |
|  | WRA |  |  |  |  |  |
|  | Men |  |  |  |  |  |
| Date (write in date) | Cluster # |  |  |  |  |  |
|  | Households |  |  |  |  |  |
|  | Refusals |  |  |  |  |  |
|  | PSC |  |  |  |  |  |
|  | SAC |  |  |  |  |  |
|  | WRA |  |  |  |  |  |
|  | Men |  |  |  |  |  |
| Date (write in date) | Cluster # |  |  |  |  |  |
|  | Households |  |  |  |  |  |
|  | Refusals |  |  |  |  |  |
|  | PSC |  |  |  |  |  |
|  | SAC |  |  |  |  |  |
|  | WRA |  |  |  |  |  |
|  | Men |  |  |  |  |  |